Progress reporting on the action plan recommendations contained in paragraphs 96-99 of the Committee of Compliance

| Field | Actions/Activities/Measures | Time Frame/Funds | Results achieved / progress | Responsible Institution |
| --- | --- | --- | --- | --- |
| Legislation | Drafting of the Decision of the Council of Ministers on procedures for public participation in decision making 1. Establishment of the Working Group to draft the Decision of the Council of Ministers which will consist of specialists from Legal Department, sector of IT and communication and Directory of Local Government (Ministry of Interior), Ministry of European Integration. 2. Identification of gaps in the legal framework in public participation in decision-making. 3 Prepare the action plan. 4. Drafting of the Decision of Prime Minister for the Public Participation 5. Discussion with NGO’s on the draft and taking into consideration their suggestions. | Short term State Budget 20 November 30 November 30 November 10 January 10 February | Working Group Established Gap analyses done. Draft action plan prepared and a copy sent to Secretariat. Draft Decision prepared. Draft ready to be send for comments to ministry lines and interested parties and NGOs | Ministry of Environment, Forests and Water Administration MoE, other ministries, interested parties and NGOs |