Unofficial translation

Confirmed

Decision of Cabinet of Ministries of Ukraine

from ___________ 2008 №_________

Action Plan

on fulfillment of the Decision of the Parties of Aarhus Convention ІІІ/6f

| Content | The responsible entity | Term of fulfillment |
| --- | --- | --- |
| Access to information, public participation in decision-making process (national level) |  |  |
| 1. Design and take for consideration by Cabinet of Ministers of Ukraine the draft of Resolution on Order of Public Participation in decision-making, which can influent on environment | Ministry of Environment Protection of Ukraine | December 2008 |
| 2. Design and take for consideration by Cabinet of Ministers of Ukraine the draft of Resolution on List of Ecological Information and Order of its Publishing by the Central and Regional Authorities | Ministry of Environment Protection of Ukraine | December 2008 |
| 3. Design Order of Ministry of Environment Protection of Ukraine which will confirm the new Statements: - on Public Participation in Decision- Making; - on Order of Access to Ecological Information. | Ministry of Environment Protection of Ukraine | December 2008 |
| 4. Design the Instruction on Order of holding the state ecological expertise | Ministry of Environment Protection of Ukraine | November 2008 |
| 5. Create of the Register of claims and conclusions on state ecological expertise, to provide their publishing on web-portal of Ministry of Environment Protection of Ukraine and its territorial units | Ministry of Environment Protection of Ukraine | December 2008 |
| 6. Design the weekly Bulletin of Ministry of Environment Protection of Ukraine in addition to «Ecotyzhden’» (claims and conclusions on state ecological expertise, other official ecological information) | Ministry of Environment Protection of Ukraine | November 2008 |
| 7. Overview Orders of Ministry of Environment Protection of Ukraine with restricted label on the subject of suitability to Aarhus Convention | Ministry of Environment Protection of Ukraine | December 2008 |
| 8. Make amendments to Resolution of Cabinet of Ministers of Ukraine from October 15, 2004 on Some Issues about the public participation in designing and realization of state policy | Ministry of Environment Protection of Ukraine | December 2008 |
| 9. Design the Statement on network of national ecological automatic informational and analytical system of granting the access to ecological information | Ministry of Environment Protection of Ukraine | November, December 2008 |
| Interauthority level |  |  |
| 10. Organize the Interauthority working group on fulfillment of the Decision of the Parties of Aarhus Convention | Ministry of Environment Protection of Ukraine Ministry of Justice Ministry of transport and connection Ministry of emergency Ministry of regional development and building регіонального Ministry of housing Ministry of industrial policy Ministry of agricultural policy Ministry of fuel and energy Ministry of health protection State Committee for land recourses State Committee for forestry State Committee for Water Recourses | October 2008 |
| Regional level |  |  |
| 11. Design a new Statement on Aarhus regional centers with determination of their legal status and other procedures | Ministry of Environment Protection of Ukraine | November 2008 |
| Seminars and workshops |  |  |
| 12. Conduct studying on implementation of Aarhus Convention in Ukraine for civil servants and judges | Ministry of Environment Protection of Ukraine jointly with State Ecological Academy of postgraduate studying and management, Academy of judges, National Academy for Civil Servants under President of Ukraine | October - December 2008 |
| 13. Conduct seminars and workshops on implementation of Aarhus Convention in Ukraine for officials of territorial and special entities of Ministry of Environment Protection of Ukraine, who are responsible for cooperation with mass-media and public | Ministry of Environment Protection of Ukraine | November 2008 |
| Scientific and methodological data |  |  |
| 14. Design and publish of scientific and methodological data | Ministry of Environment Protection of Ukraine | December 2008 |
| 15. Publish the literature for chief executives of industrial, transport, building enterprises (Booklet "Ecology and Law") | Ministry of Environment Protection of Ukraine | December 2008 |
| Amendments to Laws |  |  |
| 16. Give the proposals to make amendments to Law of Ukraine on Protection of Environment, Law of Ukraine on Ecological Expertise | Ministry of Environment Protection of Ukraine | February 2009 |
| 17. Design draft of Law which will ratify the amendment to Convention on genic-modified organisms | Ministry of Environment Protection of Ukraine | March 2009 |
| 18. Give the proposals to make amendments to Code of Ukraine on administrative delicts with the aim to strengthen the responsibility for non-granting the ecological information | Ministry of Environment Protection of Ukraine | March 2008 |