Unofficial translation

Cabinet of Ministers of Ukraine

R U L I N G

dated December 27th, 2008

# 1628-p

Kyiv

On the Approval of Action Plan on Implementation of the Decision of the Parties to Aarhus Convention #III/6f

Aimed at the implementation the provisions of Aarhus Convention, to approve the Action Plan on implementation of the decision of the Parties to Aarhus Convention #III/6f as attached.

Prime Minister of Ukraine                                                                Yulia Tymoshenko

Approved by

Ruling of Cabinet of Ministries of Ukraine

of December 27th, 2008 # 1628-p

Action Plan

on the implementation of the Decision of the Parties to Aarhus Convention ІІІ/6f

| Action | Responsibility for implementation | Terms of implementation |
| --- | --- | --- |
| 1. Designing and providing for consideration to the Cabinet of Ministers of Ukraine: |  |  |
| - Draft Laws of Ukraine: |  |  |
| - On amendments to Laws of Ukraine concerning the obligations under the Aarhus Convention | Ministry of Environmental Protection of Ukraine | September 2009 |
| - On ratification of amendments to Aarhus Convention (concerning the genetically modified objects) | Ministry of Environmental Protection of Ukraine | November 2009 |
| - Draft Rulings of Cabinet of Ministers of Ukraine: |  |  |
| - On procedure of Public Participation in Decision-Making Process concerning the environmental issues; | Ministry of Environmental Protection of Ukraine | June 2009 |
| - On procedure of Publishing the Environmental Information; | Ministry of Environmental Protection of Ukraine | June 2009 |
| - On approval of the Statement on Public Environmental Automated Informational Network for ensuring the proper access to environmental information | Ministry of Environmental Protection of Ukraine | August 2009 |
| 2. Designing and approval of the Model Statute for Regional Aarhus Centres | Ministry of Environmental Protection of Ukraine | March 2009 |
| 3. To ensure the publication of Statements and Conclusions of State Ecological Expertise on the web-portal of Ministry of Environmental Protection of Ukraine, web-sites of the regional divisions and in separate column of “Ecotyzhden’” periodical | Ministry of Environmental Protection of Ukraine | March 2009 |
| 4. Establishing of the Inter-ministerial Working Group on the implementation of the Decision of the Parties to Aarhus Convention | Ministry of Environmental Protection Ministry of Justice Ministry of Transport and Communication Ministry of Emergency Ministry of Regional Development Ministry of Housing Ministry of Industrial Policy Ministry of Agriculture Ministry of Fuel and Energy Ministry of Health Protection State Committee for Land Resources State Committee for Forestry State Committee for Water Resources | March 2009 |
| 5. To carry out the following events: |  |  |
| - lectures for civil servants and judges related to the implementation of Aarhus Convention in Ukraine | Ministry of Environmental Protection of Ukraine | During the year |
| - seminars and workshops on issues related to the access to information on environment and public participation in environmental decision-making for civil servants working with mass-media at the local level | Ministry of Environment Protection of Ukraine | September 2009 |
| 6. Designing and publishing of the scientific and methodological handbooks and manuals | Ministry of Environmental Protection of Ukraine | October 2009 |
| 15. Preparation and publishing of the booklet “Environment and Law: mechanisms of implementation of Aarhus Convention” for chief executives of enterprises in industry, transport, construction spheres etc. | Ministry of Environmental Protection of Ukraine | January 2008 |