ANNUAL progress report

| I. Project title | Strengthening the capacities of developing countries and countries with economies in transition to facilitate legitimate border crossing, regional cooperation and integration |
| --- | --- |
| II. Project DA code | 12/13AA; ROA-231-8, IMIS ID: 2922 |
| III. Executing entity | UNECE Co-operating Agencies: UNESCAP, UNESCWA, UNECA, UNECLAC |
| IV. Reporting period covered | January 2014 – December 2014 |
| V. Financial Implementation rate (in % of the total budget) | 45.8% |

## VI. SUMMARY OF ACHIEVEMENTS TO DATE

UNECE in close collaboration with UNESCAP, UNESCWA, UNECA and UNECLAC started to implement this project at the beginning of 2013. UNECE developed a project website (http://www.unece.org/trans/themes/unda_customs-to-customs.html) to improve information sharing and communications on the project objectives, activities and results.

Several countries have been considered as candidate countries for the project. These are Georgia in the UNECE region, Morocco and Tunisia in the UNECA region, Tunisia, Morocco, Jordan, and Lebanon in the UNESCWA region, Kyrgyzstan in the UNESCAP region and Costa Rica in the UNECLAC region.

In 2014, UNECE, UNESCWA and UNECA finalized the gap-analyses to accurately assess the candidate countries’ capacities to electronically exchange transit-related data with their neighboring countries. UNESCAP and UNECLAC studies are currently being finalized the intermediate results have already been presented at the first interregional Expert Group meeting.

The first interregional Expert Group meeting, which main objective was to select the pilot countries for the project, took place in Geneva on 8 December 2014. The agenda, documents, presentations and the report are available on the project website. A meeting evaluation is annexed to the report. On the basis of available “gap” analyses and of the experience of the experts present, the Expert Group selected the following countries as pilot countries for the project: Costa-Rica (UNECLAC), Georgia (UNECE), Kyrgyzstan (UNESCAP), Morocco (UNECA) and Tunisia (UNECSWA).

All RCs received financial authorizations for the fund to be used in 2014 and 2015, including for the workshops and consultancies that are currently under preparation.

## VII. Review of performance indicators and activities

Table 1 – Review of Performance Indicators

| Expected Accomplishment | Indicator of achievement (T0) | Indicator of achievement (T1) | Comments |
| --- | --- | --- | --- |
| EA1. Increased capacity to exchange secure electronic C2C transit information by the five pilot countries with their neighbouring countries and trade partners. | The five pilot countries will either start or increase the exchange of C2C electronic information on transit with neighbouring countries or trade partner by the end of 2015 or develop an Action Plan setting out the steps needed to introduce a new C2C platform to exchange information and ensure its sustainability over time. | Planned for 2015 | The engagement by the pilot countries has shown their interest in achieving the project objectives. 3 gap analyses have been completed (UNECE, UNECA and UNESCWA) and 2 are ongoing and are expected to be completed in January 2015. |
| EA2. Increased capacity to utilize international standard electronic messages in the field of transit procedures by the pilot countries and their neighbouring countries, in particular B2C information. | Five developing countries or countries with economies in transition increase or make concrete plans to increase the use of standard electronic messages for transit procedures by the end of 2015. | Planned for 2015 | The engagement by the pilot countries shows their interest in achieving the project objectives. 3 gap analyses have been completed (UNECE, UNECA and UNESCWA) and 2 are ongoing and are expected to be completed in January 2015. |

Table 2 – Review of Completed Activities

| Activities | Comment |
| --- | --- |
| A1.1 - Delivering a first inter-regional Expert Group Meeting aimed at the assessment of the legal and technical needs of candidate developing countries and countries with economies in transition to extend the exchange of electronic information with other countries (“gap” analysis). The linkages with major existing national and regional computerized transit systems will also be assessed and explored. On the basis of studies to be prepared by independent consultants, the Expert Group will determine the selection criteria and nominate at least five pilot countries. | The activity was partially completed. A website for the project was developed and launched in July 2013. (http://www.unece.org/trans/themes/unda_customs-to-customs.html) General Terms of Reference (ToR) outlining standard criteria and common principles for the gap-analysis were developed and shared with all cooperating agencies in April 2013. Region-specific TORs for the gap-analysis were prepared by all RCs. RCs hired consultants to conduct the gap analysis and the final reports in UNECE, UNECA and UNESCWA have been delivered. The first Expert Group Meeting took place on 8 December 2014, the report is available on the project website. The following pilot countries were selected: Georgia in the UNECE region, Morocco in the UNECA region, Tunisia in the UNESCWA region, Kyrgyzstan in the UNESCAP region and Costa Rica in the UNECLAC region |
| A1.2. Development and deployment of a secure C2C versatile electronic exchange platform, taking due account of the specific challenges faced by developing countries and countries with economies in transition. | The ToR are about to be finalized. Consultancy planned for 2015 |
| A1.3. Provision of technical assistance to national experts in at least five pilot countries to link national or regional Customs IT systems (e.g. ASYCUDA) to the C2C exchange platform or to development of an Action Plan setting out the steps needed to introduce a new C2C platform to exchange information and ensure its sustainability over time. | Planned for 2015 |
| A1.4. Deliverance of five technical workshops (two days) to build capacity of developing countries and countries with economies in transition to maximise the benefits offered by the C2C exchange platform, to increase their electronic exchange of Customs information with neighbouring countries as well as to adopt international standards when it comes to electronic messages (the project will provide funding for twenty participants at each workshop). | Planned for 2015 |
| A2.1 Delivering a second inter-regional Expert Group Meeting (one day) at the end of the project to present and evaluate the results achieved in the five pilot countries. | Planned for 2015 |
| A2.2 Delivering a seminar (one day and back to back with the second inter-regional Expert Group Meeting) to promote the electronic exchange of customs information and the adoption of standard electronic messages, with special focus on the specific requirement of developing countries and countries with economies in transition on the basis of the results achieved in the five pilot countries (the project will provide funding for 45 participants from developing countries and countries with economies in transition, in particular from countries other than the pilot countries). | Planned for 2015 |

- VIII.CHALLENGES/PROBLEMS ENCOUNTERED so far

Project implementation has been challenging in view of the significant differences across the participating regions.

Table 3 – Challenges and actions

| Description of challenge | Action(s) taken to solve the issue, if any |
| --- | --- |
| Most implementing agencies considered the budget initially planned for the gap-analysis consultancies as insufficient. Due to the limitation of the 2013 consultancy budget, UNESCAP could not recruit a consultant for the gap analysis. | The 604 (0140) National/Regional Consultants budget for activity 1.1. was increased from USD 18,500 to USD 25,000 (i.e. USD 3,700 to USD 5,000 to each RC). As a result a reduction of the same budget line occurs for activity A1.3. which decreased from USD 150,000 to USD 143,500 (i.e. USD 30,000 to USD 28,700 to each RC). A budget reallocation will be undertaken in 2014 to ensure sufficient funds for ESCAP’s gap analysis. |
| UNECLAC encountered problems in identifying interested candidate countries for the project. | UNECLAC liaised with the nine most active countries in the area of customs integration and presented the project to some participants in a seminar on trade facilitation that took place in Santiago on 23-26 September 2013. Uncertainties about the results of the WTO Ministerial Meeting in Bali had an impact on the countries’ reservation to join the project. Additional follow-up with these countries will be ensured. Political differences in the region may also prevent some countries from working together. If no country expresses its interest to join the project, UNECLAC will hire a consultant to conduct a gap-analysis of a group of countries in the region. Based on the results, the RC will liaise with those countries which would benefit the most from joining the project, and will advocate for their engagement. |
| Late response to questionnaires by candidate countries caused a delay in undertaking the gap analyses. | RCs used their own channels/network to facilitate and speed up the work of the consultant, including liaising with government officials in candidate countries. |

- IX.SUPPLEMENTARY FUNDING

No supplementary funding was received in 2014.

Turkey and UNECE are still looking for synergies between the UN Development Account (UNDA) project 12-13AA and the Italy-Turkey e-TIR pilot project, in particular as concerns the development and deployment of a secure C2C versatile electronic exchange platform (activity A.1.2). These synergies could lead to supplementary funding in the future.

- X.REVISIONS

The 604 (0140) National/Regional Consultants budget line for A1.1 was increased from USD 18,500 to USD 25,000 (i.e. from USD 3,700 to USD 5,000 to each RC) to ensure more funds for the gap-analysis consultancies. The same budget line for activity A.1.3 was reduced from USD 150,000 to USD 143,500 (i.e. from USD 30,000 to USD 28,700 USD to each RC).

ECLAC’s consultant budget for the gap-analysis (in 604 (0140)) was raised to USD 6,000 (from 5000USD) to take into account the fact that the selected consultant was from Argentina and had to travel to Costa Rica for interviews.

ECLAC invited two experts at the first interregional Expert Group meeting.

XI.WORK PLAN FOR REMAINING ACTIVITES

Table 4 – Remaining activities

| Remaining Activities | Start date | Date of completion |
| --- | --- | --- |
| A1.1 Delivering a first inter-regional Expert Group Meeting (two days) aimed at the assessment of the legal and technical needs of candidate developing countries and countries with economies in transition to extend the exchange of electronic information with other countries (“gap” analysis). The linkages with major existing national and regional computerized transit systems will also be assessed and explored. On the basis of studies to be prepared by independent consultants, the Expert Group will determine the selection criteria and nominate at least five pilot countries. | Started in April 2013 with the preparation of common ToR for the gap-analysis | January 2015 ( pending the finalization of the Gap Analyses in UNESCAP and UNECLAC) |
| A1.2. Development and deployment of a secure C2C versatile electronic exchange platform, taking due account of the specific challenges faced by developing countries and countries with economies in transition. | December 2014 (preparation of the ToR has started) | September 2015 |
| A1.3 Provision of technical assistance to national experts in at least five pilot countries to link national or regional Customs IT systems (e.g. ASYCUDA) to the C2C exchange platform or to development of an Action Plan setting out the steps needed to introduce a new C2C platform to exchange information and ensure its sustainability over time. | April 2015 | May 2015 |
| A1.4 Deliverance of five technical workshops (two days) to build capacity of developing countries and countries with economies in transition to maximize the benefits offered by the C2C exchange platform, to increase their electronic exchange of Customs information with neighbouring countries as well as to adopt international standards when it comes to electronic messages (the project will provide funding for twenty participants at each workshop). | March 2015 | July 2015 |
| A2.1 Delivering a second inter-regional Expert Group Meeting (one day) at the end of the project to present and evaluate the results achieved in the five pilot countries. | September 2015 | October 2015 |
| A2.2 Delivering a seminar (one day and back to back with the second inter-regional Expert Group Meeting) to promote the electronic exchange of Customs information and the adoption of standard electronic messages, with special focus on the specific requirement of developing countries and countries with economies in transition on the basis of the results achieved in the five pilot countries (the project will provide funding for 45 participants from developing countries and countries with economies in transition, in particular from countries other than the pilot countries). | September 2015 | October 2015 |

- XII.ADDITIONAL INFORMATION

UNECE developed a website for the project (http://www.unece.org/trans/themes/unda_customs-to-customs.html) to enhance the project’s visibility and to support communications concerning its objectives, activities and results.

XIII.financial information

| Object Class | Description |  | A. Budget/Allotment | B. Actual disbursements | C. Commitments outstanding | D. Total Expenditure | E. Balance Remaining | F. Revisions to allotments (if any) | G. Explanations to revisions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 602 | General Temporary Assistance |  | 37,000 | 0 | 0 | 0 | 37,000 |  |  |
| 604 | Consultants and Expert Groups | 0111-Int. consult.: | 14,700 | 0 | 0 | 0 | 14,700 |  |  |
|  |  | 0140-Nat./reg. consult.: | 168,500 | 16,694 | 124,810 | 116,504 | 26,997 |  |  |
|  |  | 2601-Consult. travel: | 19,000 | 0 | 11,200 | 11,200 | 7,800 |  |  |
|  |  | 2602-Expert Group (travel): | 27,000 | 8,009 | 2,905 | 10,914 | 16,086 |  |  |
| 608 | Travel of staff |  | 64,800 | 10 | 51,840 | 41,050 | 12,950 |  |  |
| 612 | Contractual services |  | 111,000 | 0 | 12,000 | 12,000 | 99,000 |  |  |
| 616 | Operating expenses |  | 5,500 | 0 | 3,996 | 3,596 | 1,504 |  |  |
| 618 | Supplies, Materials etc. |  | 50,000 | 0 | 0 | 0 | 50,000 |  |  |
| 621 | Fellowships, grants and contributions | 7202 - Workshops: | 252,500 | 62 | 112,000 | 112,006 | 140,494 |  |  |
|  |  | 7203 - Study Tours: |  | 0 | 0 | 0 | 0 |  |  |
|  | Total |  | 750,000 | 24,719 | 318,751 | 343,469 | 406,531 | 0 | 0 |

| Implementation rate (%) | = 45.8% |
| --- | --- |

Figures are not final

Remaining costs of a another UNECE managed UNDA project which accounts have been already closed