9TH TRANCHE UNITED NATIONS DEVELOPMENT ACCOUNT PROJECT

ANNUAL PROGRESS REPORT

PROJECT “STRENGTHENING NATIONAL CAPACITY IN MOST VULNERABLE UNECE COUNTRIES FOR SUSTAINABLE DEVELOPMENT OF STATISTICS”

| I. Project title | Strengthening national capacity in most vulnerable UNECE countries for sustainable development of statistics |
| --- | --- |
| II. Project DA code | 14/15AD; ROA-286-9; IMIS: 3026 |
| III. Executing entity | United Nations Economic Commission for Europe (UNECE) |
| IV. Reporting period covered | August – December 2014 |
| V. Financial Implementation rate (in % of the total budget) | 18 % |

## VI. Summary of achievements to date

Project implementation started in the second half of 2014. First advisory mission and one day national workshop were organised in Kyrgyzstan in October 2014. This mission responded to the country request to follow-up on implementation of recommendation from the Global Assessment (GA) of National Statistical System of Kyrgyzstan. UNECE provided support to the revision of the Law on State Statistics (LSS) in order to bring the scope and the institutional framework of official statistics fully in line with the UN Fundamental Principles of Official Statistics.

The first sub-regional workshop was organised on 10-11 December 2014 in Almaty, Kazakhstan to introduce the project, and to discuss its objectives, the implementation strategy and the monitoring tools with the beneficiary countries. The meeting also allowed participants to share ideas and current good practices in implementing recommendations provided in respective Global Assessments reports and express needs for specific technical support to be delivered in the framework of the project. The beneficiary countries were encouraged to send a request for support in implementation of five specific global assessment recommendations. Multilateral and bilateral partners were invited to contribute to the first sub-regional workshop.

Based on request for support for developing statistical laws from the beneficiary countries (namely: Armenia, Kyrgyzstan, Tajikistan and Ukraine), UNECE launched the work on the Generic Statistical Law (GSL). It was agreed that GSL will be prepared as for EECCA countries. For each proposed article, it will provide clear explanations and links to the UN Fundamental Principles of Official Statistics (UN-FPs) adopted by the UN General Assembly in 2014.

Comments/ recommendations from the UNECE (respective subprogramme/ Project Management Unit)

The project started later than expected/ in the second part of 2014. Core project activities will be delivered in 2015-2017.

## VII. Review of performance indicators and activities

Table 1 – Review of Performance Indicators

| Expected Accomplishment | Indicator of achievement (T0) | Indicator of achievement (T1) | Comments |
| --- | --- | --- | --- |
| EA1 Recommendations from Global Assessments (GAs) are endorsed by relevant national authorities and incorporated into the multiyear (strategic) and annual (operational) statistical programmes of work. | Number of target countries that have integrated the recommendations of Global Assessments into the strategic statistical programmes and, where relevant, the National Strategy for the Development of Statistics (NSDS). |  | The project started in the second part of 2014. It is too early to assess progress on this indicator. |
| EA2 Strengthened capacities to build sustainable statistical production processes that are supported by sufficient organisational structures. | Number of national statistical production processes modernized in target countries. |  | The project started in the second part of 2014. The advisory mission and activities are planned for 2015-2017. It is too early to assess progress on this indicator. |
| EA3 Increased capacity of national statistical offices to produce and disseminate internationally comparable statistics | Increased volume of internationally comparable statistics (data), including methodological notes and quality reports (metadata) that are available on the respective national statistical websites of target countries. |  | Project started in the second part of 2014. The activities are planned for 2015-2017. It is too early to assess progress on this indicator. |

Table 2 – Review of Completed Activities

| Activities | Comment |
| --- | --- |
| A1 8 advisory missions to assist national statistical authorities of beneficiary countries in the formulation and inclusion of the recommendations in their respective statistical programmes of work | 2014: Advisory mission and one day national workshop were organised in Kyrgyzstan. Other activities are planned for 2015-2017 (see Table 5). |
| A2 4 sub-regional workshops/training seminars to promote the exchange of good practices and experience among the target countries in implementing the UN Fundamental Principles and rationalizing (streamlining) the production and dissemination of official statistics. | First sub-regional was organized in Almaty, Kazakhstan on 10-11 December 2014 Other activities are planned for 2015-2016-2017. (see Table 5) |
| A3 16 national workshops/training seminars combined with advisory missions to assist target countries in building sustainable capacities for collecting, processing, analysing and disseminating internationally comparable statistics, including set-up and maintenance of online dissemination databases and user-friendly data extraction software. | Activities planned for 2015-2016-2017 will be based on discussions at the first sub-regional workshop on the implementation of recommendations from the global assessments held in Almaty on 10-11 December 2014. (see Table 5) |
| A1-3 At the end of the project, 8 advisory missions to beneficiary countries to conduct follow-up assessments of progress made and to identify remaining gaps. | All are planned for 2016-2017. |

- VIII.CHALLENGES/PROBLEMS ENCOUNTERED so far

Table 3 – Challenges and actions

| Description of challenge | Action(s) taken to solve the issue, if any |
| --- | --- |
| UNDA fund available only late in 2014 The UNDA allotment was available only in April 2014. Availability of funds in January 2014 would have allowed better implementation of the project. |  |
| Working jointly with UNDP UN rules allow only two options for logistics of a workshop. The first is procurement which represents high administrative burden and therefore, it is not suitable for the UNDA project activities. The second option is to work jointly with UNDP. However, in the case of the sub-regional workshop, the support of the UNDP Kazakhstan liaison office in Almaty was limited only to processing the payments. All other logistics had to be organised by UNECE. |  |
| Non-participation of Turkmenistan in the sub-regional workshop in Almaty, Kazakhstan The representatives of Turkmenistan confirmed his participation just a week before the event. Due to his late confirmation, it was impossible to ensure his participation. | UNECE sent several reminders to the Statistical Office of Turkmenistan. These emails were copied also to the UNDP Resident Coordinator in Turkmenistan and the representative of the Permanent Mission of Turkmenistan to the United Nations Office in Geneva. |
| Uzbekistan has not yet conducted a Global Assessment The Global Assessment is a prerequisite for full participation in the project. | Uzbekistan was encouraged to request a Global Assessment at the sub-regional workshop in Almaty, Kazakhstan. |

- IX.SUPPLEMENTARY FUNDING

Table 4 – Financial Leveraging

| Donor | Purpose | Amount raised |  |
| --- | --- | --- | --- |
|  |  | Cash (USD) | In-Kind |
| EFTA | Co-organising and co-financing sub-regional and national activities: - to increase number of organised activities, under A2 and A3; - to enhance number of archived indicators; - to finance one expert to work on the Generic Statistical Law. |  | In kind contribution to finance travel and subsistence cost for participants, experts/consultants to plan sub-regional and national activities were leveraged. Estimated amount for 2015-2016 is USD 230,000. |
| Eurostat World Bank Turkstat Rosstat | In the first sub-regional meeting (in December 2014, in Almaty, Kazakhstan), these organizations committed to support the project activities. A confirmation is expected in the first quarter 2015. |  | In kind |

- X.REVISIONS

- Not applicable.

XI.WORK PLAN FOR REMAINING ACTIVITES

Table 5 – Remaining activities

| Remaining Activities | Start date | Date of completion |
| --- | --- | --- |
| A1 8 advisory missions to assist national statistical authorities of beneficiary countries in the formulation and inclusion of the recommendations in their respective statistical programmes of work. | 2nd half 2015: Advisory mission to Kyrgyzstan. Pilot implementation of the Generic Statistical Law. Possible similar missions to Armenia, Tajikistan, Ukraine. 2016: advisory mission following a request from the beneficiary countries. | 2016 |
| A2 4 sub-regional workshops/training seminars to promote the exchange of good practices and experience among the target countries in implementing the UN Fundamental Principles and rationalizing (streamlining) the production and dissemination of official statistics. | May 2015, Istanbul, Turkey: Workshop on the implementation of 2008 SNA November 2015, Geneva, Switzerland : SEEA implementation for EECCA countries jointly with OECD/UNECE Seminar on SEEA Fall 2015, Turkmenistan: High-level seminar on e-data collection (Turkmenistan) Spring 2016, Geneva, Switzerland: Expert Group Meeting on National Accounts - Special session for Transition Economies 2016 Human Resources management and Training in Statistical Office | 2016 |
| A3 16 national workshops/training seminars combined with advisory missions (AM) to assist target countries in building sustainable capacities for collecting, processing, analysing and disseminating internationally comparable statistics, including set-up and maintenance of online dissemination databases and user-friendly data extraction software. | Fall 2015, Tbilisi, Georgia 2015: Workshop and advisory mission(AM) on the use of administrative data for the measurement of migration 2016-2017: 2 beneficiary countries to be identified: Workshop and AM of the use of administrative data for the measurement of migration 2015-2017: Other workshop/training seminar and AM to be identified following the request from the countries and outcome of the first sub-regional workshop (a kick-off of the project). | 2017 |
| A1-3 At the end of the project, 8 advisory missions to beneficiary countries to conduct follow-up assessments of progress made and to identify remaining gaps. | Planned for 2016 | 2017 |

- XII.ADDITIONAL INFORMATION

UNECE developed a Confluence Wiki page to enhance the project’s visibility and to support communications concerning its objectives, activities and results for the beneficiary countries and partner organizations. The access to the page is restricted under a user account for the moment. During the first half of 2015, UNECE will create a list of focal points in each organization of beneficiary countries with an access account. (link:http://www1.unece.org/stat/platform/display/UNDA9/Strenghening+national+capacity+in+the+most+vulnerable+UNECE+countries+for+the+sustainable+development+of+statistics, the access account for partner organization can be requested on statcoop@unece.org)

.

- XIII.financial information (in US $)

| Object Class | Description |  | A. Budget/Allotment | B. Actual disbursements | C. Commitments outstanding | D. Total Expenditure | E. Balance Remaining | F. Revisions to allotments (if any) | G. Explanations to revisions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 602 | General Temporary Assistance |  | 43,000 | 29,077 | 0 | 29,077 | 13,923 |  |  |
| 604 | Consultants and Expert Groups | 0111-Int. consult.: | 18,000 | 0 | 2,000 | 2,000 | 16,000 |  |  |
|  |  | 0140-Nat./reg. consult.: | 31,000 | 0 | 0 | 0 | 31,000 |  |  |
|  |  | 2601-Consult. travel: | 32,000 | 2,123 | 811 | 2,934 | 29,066 |  |  |
|  |  | 2602-Expert Group (travel): | 0 | 0 | 0 | 0 | 0 |  |  |
| 608 | Travel of staff |  | 72,000 | 11,510 | 1,815 | 13,325 | 58,675 |  |  |
| 612 | Contractual services |  | 25,000 | 0 | 0 | 0 | 25,000 |  |  |
| 616 | Operating expenses |  | 6,000 | 424 | 0 | 424 | 5,576 |  |  |
| 618 | Supplies, Materials etc. |  | 40,000 | 0 | 0 | 0 | 40,000 |  |  |
| 621 | Fellowships, grants and contributions | 7202 - Workshops: | 268,000 | 38,229 | 10,472 | 48,701 | 219,299 |  |  |
|  |  | 7203 - Study Tours: | 0 | 0 | 0 | 0 | 0 |  |  |
|  | Total |  | 535,000 | 81,363 | 15,098 | 96,461 | 438,539 |  |  |

| Implementation rate (%) 18.03 % | = Expenditure (D)/Budget (A) 96 461/535 000 |
| --- | --- |