## Sheet1
Pedestrian Safety GTR Preparation Schedule (Draft) | [6 empty] | INF GR / PS / 57
| 2003 |  |  |  | 2004 | [6 empty] | Remarks
| Sep. | Oct. | Nov. | Dec. | Jan. | Feb. | Mar. | Apr. | May | Jun. | Jul.
Contracting Parties
NGO
WP29 | 2003 Nov.: #131 WP29 Proposals approved; 2004 Mar.: #132 WP29; 2004 Jun.: #133 WP29
GRSP | 2003 Dec.: #34GRSP; 2004 May: # 35 GRSP
Pedestrian Safety Inf. Gr | 2003 Sep.: #５ 9/10-12; 2004 Jan.: #6
IHRA
| Test methods reviewed including threshold values |  |  |  |  | Requirements reviewed
EU and Japanese Proposals brought back and test methods reviewed including threshold values, cost effectiveness and benefit
Leg test method adopted
Head test method
First draft completed
(Must be better than the proposal by WG17 in 1998)
EU
GTR proposals worked out and presented to WP29
Reflected
Feasibility study
- Test method adopted
- Requirements reviewed
EU
Phase 2 review started
Comments of the member sates and NGOs drawn together
Report
Report
Report
Phase 2
Technical regulations adopted
GTR draft proposals reviewed
GTR draft proposals reviewed
Comments of the member sates and NGOs drawn together
Proposal
Lending impactors to the member states started
Lending impactors to member states completed
Specifications published
#7
Impactor improvement period
CCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCCC
CC
CC
CC
CC
CC
CC
CC
CC
EU
WITHDRAWN