## Sheet1
PVGTR2004-14 BEST TIMING | 2004 | [11 empty] | 2005 | [11 empty] | 2006
Quarter | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 1 |  |  | 2 |  |  | 3 |  |  | 4
MONTH | J | F | M | A L | M | J | J | A W | S | O | N | D P | J | F | M T | A | M | J | J P | A | S | O | N | D P | J | F | M | A | M | J | J | A | S | O | N | D
GRRF |  | G |  | swg1 |  |  |  | swg2 | G |  |  | swg3 |  | G | swg4 |  |  |  | swg5 |  | G |  |  | swg6 | bar: 1 F; 3 S
Report by Chairman of GRRF to AC 3 | bar: 1 M; 2 J; 4 N
Preliminary meetings
Submission of Justification to AC 3
Initial prioritising of topics
Sub-working group meeting
Further prioritising of topics
Resolution of difficult items
Preparation of 1st draft of GTR
Considertion of 1st draft by GRRF
Infomral group to agree handling
AC3 to consider Justification
Sub-working group meeting
Refiningt 1st draft of GTR
Sub-working group meeting
Prioritising of remaining issues
Preparation of 2nd draft of GTR
Sub-working group meeting
identifying final outstanding issues and handling
Resolving final issues
Report to GRRF
Sub-working group FINAL meeting
Preparation of final draft GTR | bar: 1 J
Final draft GTR to GRRF & informal group. | bar: 1 J to 1 F
Final editing | bar: 1 J
Report by Chairman of GRRF to AC 3 | bar: 1 M
Final sign off by GRRF | bar: 1 F
Submission of GTR as formal document to AC 3 | bar: 1 M
Consideration of final GTR | bar: 2 A