GLOBAL TECHNICAL REGULATION

HEAD RESTRAINTS

Schedule of Activities

# Milestones:

- 2004

  - November - The US will propose the Head Restraint GTR at the WP.29 meeting.

  - December - At the GRSP meeting, the US will announce the formation of a working group to develop the GTR.

- 2005

  - February 1-2:  Informal working group meeting (Paris, France)

  - April 11-13:  Informal working group meeting (Paris, France)

  - May:  1st Progress report submitted to GRSP

  - June 13-15:  Informal working group meeting in conjunction with ESV (Washington DC)

  - September 7-9:  Informal working group meeting (3-4 days) (Cologne, Germany)

  - December

    - 2nd Progress report and draft GTR submitted to the GRSP

    - ½ day informal working group meeting in conjunction with GRSP

- 2006

  - February

    - Informal working group meeting (3-4 days)

    - GTR submitted as formal document for translation

  - May

    - 3rd Progress report and GTR submitted to GRSP

    - ½ day informal working group meeting in conjunction with GRSP

    - The working group will present the GTR as a formal document at the GRSP meeting.

  - November - The GTR will be presented for vote to the WP.29.