## WLTP-03-05
Submitted by the WLTP Drafting Group |  |  |  | Informal Document No. WLTP-03-05
(3rd WLTP meeting, 10 June 2009)
WLTP Roadmap Appendix - Estimated Resources
| Drafting Group/TS |  |  | ACEA
Item | Cost | Manpower | Manpower cost | assumption | costs | manpower | manpower costs | Comments
Meetings 2009 - 2013 | 0 | 0 | 0
57th GRPE | 0 | 0 | 0
58th GRPE | 0 | 0 | 0
59th GRPE | 0 | 0 | 0
60th GRPE | 0 | 0 | 0
Interim Informal Group Meeting | 0 | 0 | 0
62nd GRPE | 0 | 0 | 0
63rd GRPE | 0 | 0 | 0
64th GRPE | 0 | 0 | 0
65th GRPE | 0 | 0 | 0
66th GRPE | 0 | 0 | 0
161st WP.29 | 0 | 0 | 0
Meetings 2014 - 2016 | 0 | 0 | 0
68th GRPE | 0 | 0 | 0
69th GRPE | 0 | 0 | 0
70th GRPE | 0 | 0 | 0
167th WP.29 | 0 | 0 | 0
71st GRPE | 0 | 0 | 0
72nd GRPE | 0 | 0 | 0
170th WP.29 | 0 | 0 | 0
Phase I Reports | 0 | 0 | 0
Report I-1 | 0 | 0 | 0
Report I-2 | 0 | 0 | 0
Report I-3 | 0 | 0 | 0
Report I-4 | 0 | 0 | 0
Report I-5 | 0 | 0 | 0
Report I-6 | 0 | 0 | 0
Report I-7 | 0 | 0 | 0
Report I-8 | 0 | 0 | 0
Phase II Reports | 0 | 0 | 0
Report II-1 | 0 | 0 | 0
Report II-2 | 0 | 0 | 0
Report II-3 | 0 | 0 | 0
Report II-4 | 0 | 0 | 0
Phase III Reports | 0 | 0 | 0
Report III-1 | 0 | 0 | 0
Report III-2 | 0 | 0 | 0
Report III-3 | 0 | 0 | 0
Report III-4 | 0 | 0 | 0
0. Roadmap Making Phase | 0 | 0 | 0
0.1. Make Roadmap | 0 | 0 | 0
1. Phase I - Test Procedure
1.1. DHC Team Work
1.1.1. in use data collection
1.1.1.1. Preparation |  | 500 | 50000 | 2 weeks per region |  | 400 | 40000
assumption 5 CPs |  | 2000 | 200000
1.1.1.1.1. review current process data
1.1.1.1.2. selection of test vehicles
1.1.1.1.3. selection of areas, road types, test conditions and routes
1.1.1.1.4. planning
1.1.1.2. data collection | 130000 | 160 | 16000 | vehicle costs | 450000
assumption 15 cities | 1820000 | 2240 | 224000 | driver costs |  | 6000 | 480000
1.1.1.3. data check and review |  | 1500 | 150000 | 100 hours per region |  | 500 | 50000 | 3 institutes: JARI, EPA, FIGE
1.1.1.4 statistical data |  | 150 | 15000 | 1 week per region |  | 200 | 20000
|  |  |  | 100 hours analysis |  | 100 | 10000
1.1.2. additional data collection if necessary
1.1.3. data analysis methodology
1.1.3.1. initial development | 1200 | 500 |  | 2 trips + 600 hours | 4000 | 600 | 60000
1.1.3.2. modification | 1200 | 250 |  | 2 trips + 400 hours | 4000 | 400 | 40000
1.1.4. Develop new driving cycle
1.1.4.1. development of initial mode | 2400 | 2000 |  | 4 trips + 2*240 hours | 8000 | 480 | 48000 | 2 institutes:
1.1.4.1.1. mode structure
1.1.4.1.2. mode duration
1.1.4.1.3. weighting factor (urban, rural, motorway)
1.1.4.1.4. number of short trip/idling
1.1.4.1.5. gearshift points
1.1.4.1.6. OBD impact
1.1.4.2. modification | 2400 | 2000 |  | 4 trips + 2*160 hours | 8000 | 320 | 32000 | 2 institutes:
1.1.4.2.1. weighting factor (urban, rural, motorway)
1.1.4.2.2. arrangement of short trip/idling
1.1.4.2.3. gearshift points
1.1.4.2.4. cold/hot start
1.1.4.3. final modification | 1200 | 1500 |  | 2 trips + 2*100 hours | 4000 | 200 | 20000
1.1.5. Validation tests
1.1.5.1. preparation |  | 160
1.1.5.1.1. test items
1.1.5.1.2. test vehicle matrix
1.1.5.1.3. procure test vehicles |  |  |  |  | 25000
1.1.5.1.4. test site preparation
1.1.5.2. Validation 1 (current test procedure) | 50000 | 320 |  | 3 tests, 10 vehicles | 36000
1.1.5.3. Validation 2 (new test procedure) | 300000 | 2000 |  | 3 rounds of 3 tests, 10 vehicles | 115800
|  |  |  | 3 rounds of 3 evap tests, 5 vehicles | 292500
1.1.5.4. validation test analysis
1.1.6. confirmation tests / RR
1.1.6.1. preparation |  | 80
1.1.6.1.1. test items
1.1.6.1.2. test vehicle matrix
1.1.6.1.3. procure test vehicles |  |  |  |  | 5000
1.1.6.1.4. test site preparation
1.1.6.2. confirmation tests | 40000 | 200 |  | 1 test, 5 vehicles | 7300
1.1.6.3. Round Robin
1.1.6.3.1. test items
1.1.6.3.2. test vehicle matrix
1.1.6.3.3. procure test vehicles |  |  |  |  | 50000
1.1.6.3.4. RR tests | 50000 | 200 |  | 1 test, 2 vehicles / lab | 73000
|  |  |  | transport | 180000
|  |  |  | controlling engineer 3 days per lab | 50000 | 3000 | 300000
1.1.6.3.5. correlation between labs
1.1.6.4. small modification to driving cycle
1.2. DTP Team Work
1.2.1. Terminology |  | 800
1.2.2. Test procedure | 30000 | 2000 |  |  | 100000 |  |  | ISO
1.2.2.1. emission constituent
1.2.2.2. inertia weight class
1.2.2.3. road load measurement
1.2.2.4. Pre conditioning / state of charge
1.2.2.5. electric load
1.2.2.6. calculation formulae
1.2.2.7. (Alternative fuelled vehicles (FFV, CNG, LPG, H2)
1.2.2.8. hybrid vehicle (HEV, PHEV)
1.2.2.9. electric vehicle (BEV, FCV)
1.2.2.10. Energy consumption / CO2
1.2.2.11. establish list of required reference fuels
1.2.3. Test Equipment | 30000 | 2000 |  |  | 100000 |  |  | ISO
1.2.3.1. chassis dynamometer
1.2.3.2. analyser/CVS/tunnel
1.2.3.3. others (fan, cylinder gas, SHED, …..)
1.2.3.4. minimum investment
1.2.4. Modify
1.3. engine operation outside driving cycle
1.3.1. OCE pre work: develop candidate off cycle mode
1.3.1.1. defeat device strategy |  | 1500 |  | 2 trips | 4000 | 1500 | 150000 | institute:
1.3.1.2. OCE mode definition |  | 500 |  | 1 trip | 2000 | 500 | 50000 | institute:
1.3.2. evaluation of candidate off cycle mode
1.3.2.1. develop defeat strategy
1.3.2.2. deficiencies
1.3.2.3. exemptions
1.3.2.4. extreme ambient conditions
1.3.2.5. driver selectable switch
1.3.3. comparison test method |  |  |  | 3 trips | 6000
1.3.3.1. mode driving | 10000 | 250 |  |  |  | 250 | 25000
1.3.3.2. engine mapping | 10000 | 250 |  |  |  | 250 | 25000
1.3.4. develop test procedure |  | 500 |  |  |  | 500 | 50000
1.3.5. OBD impact |  |  |  | 1 vehicle, 3 tests | 4600 | 40 | 4000
1.3.6. validation test
1.3.6.1. test vehicle selection
1.3.6.2. procure vehicles |  |  |  |  | 30000
1.3.6.3. testing | 50000 | 320 |  | 10 vehicles, 10 tests, 3 weeks | 150000 | 1600 | 160000
1.3.7. modify
1.4. MAC
1.4.1. MAC fundamental-Works
1.4.1.1. EU
1.4.1.2. Japan (2010 ~)
1.4.1.3. USA (SC03)
1.4.2. MAC Evaluation procedure
1.4.2.1. comparison test method
1.4.2.1.1. full environmental cell | 150000 | 500 | 50000 | 5 vehicles, 6 tests, 2 weeks | 307000
1.4.2.1.2. AC component evaluation |  |  |  | 50 components, 1 per day | 125000 | 240 | 24000
1.4.2.1.3. AC system evaluation |  |  |  | 10 components, 1 per day | 25000 | 80 | 8000
1.4.2.1.4. simulation |  |  |  |  | 700000
1.4.2.1.5. appropriate investment
1.4.2.1.6. influence on emissions and fuel consumption | 100000 | 500 | 50000
1.4.2.2. develop test procedure |  | 500 |  |  | 100000
1.4.2.3. validation test | 50000 | 320 | 32000 | 3 vehicles, 6 tests, complex tests (as evap) | 123000
1.4.2.4. OBD impact |  |  |  | 1 vehicle, 3 tests | 4600 | 40 | 4000
1.4.2.5. modify
1.5. gtr I Text development |  | 1600 | 160000
1.5.1. informal gtr I text
1.5.2. formal gtr I text
1.6. impact assessment
2. Phase II
2.1. OBD
2.1.1. evaluation of existing regulations
2.1.2. text development
2.1.2.1. OBD specific definitions
2.1.2.2. purpose and limitation
2.1.2.3. monitoring requirements
2.1.2.4. demonstration
2.1.2.5.information
2.1.3. validation
2.1.3.1. procure test vehicles
2.1.3.2. validation on test bench |  |  |  |  | 1202000
2.1.3.3. in-field validation |  |  |  | 20 weeks, 10 vehicles | 200000 | 320 | 32000
2.2. Low ambient temperature
2.2.1. set test condition
2.2.2. define fuel specification
2.2.3. validation |  |  |  | 5 vehicles, 3 tests, 1 temp | 36300 | 80 | 8000
2.3. High altitude
2.3.1. set test condition
2.3.2. define fuel specification
2.3.3. validation |  |  |  | 5 vehicles, 3 tests, 1 press | 36300 | 80 | 8000
2.4. Durability
2.4.1. whole vehicle durability
2.4.1.1. review current and new WLTP cycle (develop durability driving cycle)
2.4.1.2. test points
2.4.1.3. test fuel
2.4.2. bench ageing tests
2.4.2.1. define emission control parts
2.4.2.2. develop bench ageing method
2.4.2.3. test fuel
2.4.3. develop test procedure
2.4.4. validation
2.4.4.1. bench tests |  |  |  |  | 600000
2.4.4.2. road/chassis dyno |  |  |  |  | 1600000
2.4.5. assigned DFs
2.4.6. modify
2.5. ISC
2.5.1. vehicle selection criteria
2.5.1.1. define engine family
2.5.1.2. rejection criteria
2.5.1.3. number of test vehicles
2.5.1.4. odometer criteria
2.5.2. in service testing
2.5.2.1. as received condition
2.5.2.2. OBD information
2.5.2.3. conduct maintenance if necessary
2.5.2.4. second test if necessary
2.5.2.5. measured emission constituents (tailpipe, CO2, Evap., …)
2.5.2.6. test fuels
2.5.3. pass/fail judgement
2.5.3.1 number of sample
2.5.3.2. engine family
2.5.4. modify
2.6. gtr text Phase II
2.6.1. informal texts (emissions & OBD)
2.6.2. formal texts
2.6.3. impact assessment
3. Phase III
3.1. define reference fuel specifications
3.2. Correlation testing
3.2.1. specify test vehicles |  |  |  | 10 vehicles, 3 tests, 4 cycles + cold + high + evap + OCE
3.2.2. procure test vehicles |  |  |  |  | 200000
3.2.3. comparative testing |  |  |  | 20 weeks | 1620000
3.3. definition of emissions limits & OBD thresholds
3.4. final gtr text
3.5. impact assessment
Phase I | 2828400 |  |  | Phase I | 3093800 | 17200 | 1600000 | 4693800
Phase II | 0 |  |  | Phase II | 3674600 | 480 | 48000 | 3722600
Phase III | 0 |  |  | Phase III | 1820000 | 0 | 0 | 1820000
Total | 2828400 | 0 |  | Total | 8588400 | 17680 | 1648000
|  |  |  | Total Project Cost | 10236400