## Dec 2008
Schedule of Head Restraint gtr Phase-2 Informal Working Group Based on WP29/2009/130(Japan) and WP.29-149-30(Japan) Rev.2 (3-Feb.-'10) | [7 empty] | Year | '08 |  | '09 | [10 empty] | '10 | [11 empty] | '11+ (Tentative)* | [11 empty] | '12+ (Tentative)*
[8 empty] | WP29 | 11 (146) |  | 2 | 3 (147) | 4 | 5 | 6 (148) | 7 | 8 | 9 | 10 | 11 (149) |  | 1 | 2 | 3 (150) | 4 | 5 | 6 (151) | 7 | 8 | 9 | 10 | 11 (152) | 12 | 1 | 2 | 3 (153) | 4 | 5 | 6 (154) | 7 | 8 | 9 | 10 | 11 (155) | 12 | 1 | 2 | 3 (156) | 4 | 5 | 6 (157) | 7 | 8 | 9 | 10 | 11 (158) | 12
[8 empty] | GRSP |  | 12 (44) |  |  |  | 5 (45) | [6 empty] | 12 (46) |  |  |  |  | 5 (47) | [6 empty] | 12 (48) |  |  |  |  | 5 (49) | [6 empty] | 12 (50) |  |  |  |  | 5 (49) | [6 empty] | 12 (50)
General Schedule | [9 empty] | ToR Proposal |  | ToR approval |  | PR #1 | [6 empty] | PR #2 |  |  |  |  | PR #3 | [6 empty] | I/D Final PR |  |  |  |  | GRSP approval | [5 empty] | WP29 voting |  | Publication
Informal face-to-face meeting for research/validation and development | [10 empty] | #1 BASt |  |  | #2 UN |  | #3 ESV |  |  | #4 Japan |  | #5 UN |  |  |  |  | #6 UN |  |  |  | #7 |  |  | #8 UN |  |  |  |  | #9 UN |  | #10 |  |  |  | #11 UN
Development supported by Web meetings to develop regulatory text
General Schedule | [8 empty] | TOR Proposal | [5 empty] | ToR Pre approval |  |  |  |  | ToR approval | [5 empty] | PR #1 | [5 empty] | PR to WP #1 | PR #2 |  |  |  |  | PR Final | PR to WP #2
Informal face-to-face meeting for research/validation and development | [10 empty] | #0-1 10-11th @BASt |  | GBUM | #0-2 26th @ISO | GBUM | GBUM | GBUM | GBUM | GBUM | #0-3 6th @NHTSA | #1 7th @UN | GBUM | #2 2-3rd @JP | BR TEG | BR TEG | #3 17th @UN | BR TEG |  | BR TEG? | #4 20-21st @BASt |  |  | #5 (UN) | #6 (TBD) |  |  |  | #7 (UN)
Research Items |  |  | Research Institute | [5 empty] | Research/Validation Completion and Submission of Draft Proposal (Estimate)
| V = Research ongoing/planned V(Comp.)= Research completed |  | Japan | EEVC | NHTSA (US) | Korea | OICA (PDB FOAD) | Dummy supplier [Denton/FTSS]
Head restraint height | Effective height definition |  |  | V | V | [15 empty] | ----- |  | ----- | Inform questoon |  | Respons question | [11 empty] | Submission to GRSP | [5 empty] | Vote at WP29
| Height requirements |  |  | V | V | V | [14 empty] | ----- |  | ----- | ----- |  | ----- |  |  |  | -----
Low Speed Dynamic test for minor neck injury including long term consequence (up to WAD2) | Test Conditions Definition | Sled Pulse (value, conditions) | V | V | V | [5 empty] | ----- |  |  | ----- | ----- |  |  |  |  | ----- | ----- |  | ----- | ----- |  | Review Euro NCAPdelta V=16 or 18km/h or 202a
| Minor neck injury mechanism | Accidents analysis | V | V | [6 empty] | ----- |  |  | ----- | ----- |  |  |  |  | ----- | ----- |  | -----
|  | Volunteer tests/simulations | V | V | V | [5 empty] | ----- |  |  | ----- | ----- |  |  |  |  | ----- | ----- |  | ----- | ----- |  | ----->
| Evaluation indicators | Relative movements of upper/lower neck and the force on them | V | V | V | V | [13 empty] | ----- |  |  | ----- | ----- |  | Select reasonable indicators from Japan or EEVC or US
| Reference value definition |  | V | V |  | V | [13 empty] | ----- | [6 empty] | ----- |  |  |  |  | ----- | ----- | ----->
| Effects on reduction of injury and cost Effectiveness evaluation |  | V | V
|  | New HRMD Drawing |  |  |  |  | V | [15 empty] | ----- |  |  | Draft
| Bio RID II TEG | Drawing package (2D and 3D) | [5 empty] | V |  |  | ----- |  | ----- | ----- | ----- | ----- | ----- | ----- | ----- | ----- |  | ----- | ----- |  |  | Draft
|  | Certification procedures | V | V | V | V | V | V |  |  | ----- |  | ----- | ----- | ----- | ----- | ----- | ----- | ----- | ----- | ----- | ----- | ----- | ----- | ----- | Draft(pulse & W or W/O HR)
|  | Biofidelity | V | V | V | [5 empty] | ----- | [8 empty] | ----- | [5 empty] | US review EEVC evaluation
|  | Repeatability & Reproducebility | V | V |  | V | V | V |  |  | ----- | [9 empty] | ----- | ----- | ----- | -----> | -----> | Review latest result
|  | Sitting method (for standard seat) | V | V |  |  | V | V |  |  | ----- |  |  | ----- | [5 empty] | ----- | ----- |  | ----- |  |  | Review seating with design torso angle
|  | Sitting method (for Upright seat) | V | V | V |  | V | V | [5 empty] | ----- | ----- | ----- | ----- | ----- | ----- | ----- | ----- | ----- | ----- | ----- |  | ----- | ----- |  |  | ----- |  | ----- | ----->
Mid or High speed Dynamic test for other injuries (AIS 2+), | Test Conditions Definition | Whole vehicle or seat on sled |  |  | V | [20 empty] | TOR proposal to GRSP from the US | [5 empty] | Decision at WP29 for development of a high speed test
|  | Sled Pulse (value, conditions) |  |  | V
| Other injury mechanism | Accidents analysis |  |  | V
|  | Volunteer tests/simulations |  |  | V
| Dummies | Test method, structure (improve reproducibility) |  |  | V
|  | Sitting method (reduce variation) |  |  | V
| Evaluation indicators |  |  |  | V
| Reference value definition |  |  |  | V
| Effects on reduction of injury and cost Effectiveness evaluation |  | V | V
V
* These timings should be considered as indicative at this moment. The delivery of regulatory proposals will be dependant upon the completion of a collaborative programme to validate the test tools and protocols.
The informal group will regularly report progress to WP29/GRSP and agree a delivery timeline by the end of 2009.