## English
Transmitted by the expert from Japan | [16 empty] | Infromal document No. IWVTA-02-03
(2nd IWVTA IG, 18 June 2010)
Work Schedule for IWVTA informal group
| Month/Year | 2010 | [11 empty] | 2011
| Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
WP29 | bar: 2010 3; 2010 6; 2010 11; 2011 3; 2011 6; 2011 11
Inf.G | bar: 2010 3; 2010 6; 2010 11; 2011 1; 2011 3; 2011 6; 2011 11
IWVTA Inf. G
1 | Confirm members | bar: 2010 6
2 | Consider discussion items and Confirm working schedule | bar: 2010 6
3 | Consider items list / basic concept | bar: 2010 6
4 | Consider additional elements | bar: 2010 6
5 | Consider elements to be addressed in the review of the 1958 Agreement | bar: 2010 6
6 | Confirm technical requirement items/ basic concept | bar: 2010 11
7 | Confirm additional elements | bar: 2010 11
8 | Confirm review of the 1958 Agreement | bar: 2010 11
9 | Propose draft roadmap | bar: 2010 11
10 | Discuss road map in detail | bar: 2011 3; 2011 6
11 | Discuss content of review of the 1958 Agreement in detail | bar: 2011 3
12 | Consider necessity of working group Study budget if necessary | bar: 2011 3; 2011 6
13 | Decide budget policy if necessary | bar: 2011 6
14 | Confirm content of review of the 1958 Agreement | bar: 2011 6
15 | Confirm final road map as Informal group | bar: 2011 6
16 | Final confirmation | bar: 2011 6
17 | Confirm draft proposal review of the 1958 Agreement in detail | bar: 2011 11