| WLTP DHC subgroup |  |
| --- | --- |
| Date | 08/01/10 |
| Title | Actions on open issues |
| Working paper number | WLTP-DHC-02-16 |

- Introduction

- This document describes the counter-proposal on open issues raised up during 1st DHC meeting.

- Open issues

Request to extend the data collection schedule by 4 months.

During 1st DHC meeting, some of data collection Contracting Parties raised up the concern on deadline of data collection schedule due to administrative process and/or others. At the same time, it was also requested to keep the original schedule to develop the initial cycle as planned.

- Counter-Proposal

This section provides the counter-proposal by reviewing the data processing process in detail and the data collection plan by each Contracting Party.

  - Data processing

Fig 1.  Data processing flow

Table 1.

| number | contents | duration | remark |
| --- | --- | --- | --- |
| (1) | Confirm collected data | 20 working days |  |
| (2) | Filtering, and/or thinning |  | if necessary |
| (3) | Generate database（Idling & ST） |  |  |
| (4) | Generate distribution, others |  |  |
| (5) | Check, summary, comparison |  |  |

It takes approximately 20 working days to complete data processing for each region.

  - Data collection plan

According to each Contracting Parties plan (WLTP-DHC-02-11, submitted by Korea and WLTP-DHC-02-10, submitted by Japan), data collection will be completed by

End of July, 2010 (Korea)

End of May, 2010 (Japan).

  - Counter-Proposal schedule

Table 2 shows the revised schedule for data collection and data processing.

- Since Japan will complete the data collection by May 2010, start data processing from June 2010, earlier by 3 months than original plan.

- Then Korea will complete the data collection by July 2010, conduct data processing in August 2010.

- Other regions should submit data in due order

by August 2010        : at least 3 regions data should be available

by September 2010  : at least 4 regions data should be available

by October 2010       : at least 5 regions data should be available

by November 2010   : at least 6 regions data should be available

by December 2010   : all regions data should be available

As a result, initial cycle development can be completed by March 2011 as planned.

Table 2.  Revised Schedule