## Sheet1
Roadmap for IWVTA
[5 empty] | Month/Year | 2010 |  |  |  | 2011 | [11 empty] | 2012 |  |  | 2013 |  |  | 2014 |  |  | 2015 |  |  | 2016 | 2017-
[5 empty] | Item | 3 | 6 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 3 | 6 | 11 | 3 | 6 | 11 | 3 | 6 | 11 | 3 | 6 | 11 | 3
[5 empty] | WP29 | X | X | X |  |  |  | X |  |  | X |  |  |  |  | X |  | X | X | X | X | X | X | X | X | X | X | X | X | X
[5 empty] | Inf.G | X | X | X |  | X |  | X |  |  | X |  |  | X? |  | X
List of items to be discussed for IWVTA
Proposal & agreement on roadmap | [7 empty] | ○ | [11 empty] | ü
1 | Consideration of elements necessary for the IWVTA system
(a) Issues related to definitions
|  |  | Necessity to enable ECE adoption for M1 alone for IWVTA purposes | [8 empty] | ü
|  |  | Discussion on scheme that will enable ECE adoption for M1 alone for IWVTA purposes | [16 empty] | ü
|  |  | Necessity to discuss clarification of M1 in the scope of IWVTA (definitions of M1, N1-converted M1, division between M1 and N1) | [8 empty] | ü
|  |  | Discussion on clarification of M1 in the scope of IWVTA (definitions of M1, N1-converted M1, division between M1 and N1) | [16 empty] | ü
|  |  | Discussion on definition of vehicle types, categories, etc. (INF-G?) | [18 empty] | ○ | [11 empty] | ü
(b) Issues related to type-approval procedures
|  |  | Framework for discussing application documents and procedures for change | [16 empty] | ü
|  |  | Discussion on and proposal on application documents and procedures for change (INF-G?) | [18 empty] | ○ | [11 empty] | ü
|  |  | Development of draft provisions on details of application management for the whole vehicle approval, including composition of application documents, certificate of conformity, list of approval numbers, and vehicle identification information (INF-G?). | [22 empty] | ○ | [7 empty] | ü
(c) Issues related to technical requirements
|  |  | Proposal & agreement on the list of regulations applicable to IWVTA and on framework for discussing the list |  |  |  |  | ○ | [11 empty] | ü
|  |  |  | Consolidation of lists of national requirements of each CP＠Inf-G (11/2010) |  |  |  | ○
Development of the draft list of applicable regulations (first proposal)
|  |  |  | Presentation of the first proposal of the draft list of applicable regulations and request of comments from CPs＠Inf-G (1/2011) | [5 empty] | ○
|  |  |  | Presentation of comments from CPs (need to be summarized in advance)＠Inf-G (3/2011) | [7 empty] | ○
Development of the draft list of applicable regulations (second proposal)
|  |  |  | Presentation of the draft list of applicable regulations (second proposal) and request of comments from CPs＠Inf-G (6/2011) | [10 empty] | ○
|  |  |  | Summarization of comments from CPs and the list of regulations applicable to IWVTA (final proposal) | [15 empty] | ü
|  |  |  | Framework for discussing the list of regulations applicable to IWVTA | [10 empty] | ○ |  |  |  |  | ü
|  |  | Work for developing and amending ECE regulations for establishment of IWVTA (each GR) | [18 empty] | ○ | [11 empty] | ü
2 | Revision of the 1958 Agreement related to IWVTA (if necessary)
|  |  |  | Review of points in question and discussion on the necessity of revision | [5 empty] | ○
|  |  |  | Finalization of item to be consider for revision of the 1958 Agreement | [10 empty] | ○ |  |  |  |  | ü
3 | Basic concept
|  |  |  | Concept of ECE 0 (IWVTA) submitted by OICA |  |  |  | ○ |  |  |  | ○ | [21 empty] | ü
IWVTA common basis establishment Phase
○: Proposed
ü: Agreed
→: Work in progress
2nd Step
＠Informal Group under WP29
ROADMAP Making Phase