## Slide 1: Report of 6th DTP Meeting to GRPE 9th June 2011 UNECE, Geneva (CH)
Air Pollution Control and NIR Division
Informal document No. GRPE-62-15
(62 GRPE, 7-10 June 2011, agenda item 3(a))
Notes: <number>

## Slide 2: Content of the report
Background information
Meetings since last GRPE
Agenda of 6th DTP
General issues DTP
Subgroup reports
Planning of validation phase 2
Next steps

## Slide 3: Background information to DTP6
Mr. Krause, secretary of DTP, was unfortunately not present at the meeting for health reasons.
Working progress is very good, nevertherless still many open issues remain to be solved until GRPE in January.
Draft definitions as well as draft partial test procedures are available but not consolidated yet.
GTR manager is not available yet. Start of GTR drafting not possible soon.
Final planning of validation phase 2 is an urgent matter now.
Relevant set of parameters for implementation of validation phase 2 have to be provided very soon.

## Slide 4: Previous meetings of DTP
5th DTP (DTP5) from 12th to 14th April 2011 at EMPA in Dübendorf near Zürich
  => minutes see document WLTP-DTP-05-11
6th DTP (DTP6) yesterday on 8th June 2011
Documents available on UNECE WLTP website under
DTP5th and DTP6th as well as on EU circa website.

## Slide 5: Minutes DTP5 (wrap-up and open issues)

## Slide 6: Minutes DTP5 (wrap-up and open issues)

## Slide 7: Agenda of 6th DTP on 8th June 2011

## Slide 8: General issues DTP (ICE progress report)
1. Test temperature (results from UTAC and JRC)
2. Inertia classes (presentation by icct and OICA)
3. Vehicle test mass (presented by NL)
4. Family concept (not handled, postponed)
These issues are not essential for validation phase 2
The approach is to have further consolidated discussions at DTP7 in September.
Contracting parties are invited to express their views on these issues until DTP7.
In particular, have a consolidated EU position on temperature by DTP7.

## Slide 9: Subgroup reporting
Reports given from LabProcICE, PM/PN, AP and LabProcEV as well as EU study on EV.
Working progress regarding open issues and GTR drafting has been shown.
Issues not absolutely relevant for validation phase 2 will be discussed after consolidation at DTP7.
Relevant parameter needed for validation phase 2 have been addressed within the subgroup.
No advice required from DTP so far.
Subgroups agreed to deliver set of parameters needed for validation phase 2 by end of July.

## Slide 10: Overview planning of validation phases
Source: Validation Task Force, lead JRC

## Slide 11: Agreed objectives for validation phase 2

## Slide 12: Interested parties for validation phase 2
Party Laboratory
China, participation to be confirmed
EU JRC
France UTAC
Germany probably Tuev-Nord
India, participation to be confirmed
Japan NTSEL, JARI, JAMA
Korea NIER
Netherlands to be defined
South Africa SABS
Switzerland EMPA and AFHB to be confirmed
AECC to be defined
OICA to be defined
-> Final confirmation needed by end of June to DTP chair!

## Slide 13: Draft test matrix for validation phase 2
Draft test matrix presented by Ichikawa-san.
Matrix containing number of labs, type of vehicles and parameters to be tested.
Matrix has to be considered as starting point for the detailed planning.
Detailed planning is going to be elaborated by validation task force.
DTP agreed on the principle for both objectives and test matrix for validation phase 2.

## Slide 14: Next steps
Final confirmation from parties and laboratories regarding participation in validation phase 2 by end of June
Subgroups provide set of parameters for validation phase 2 by end of July.
Validation task force will provide a laboratory guidance for validation phase 2 by end of July.
Next DTP meeting (7th) from 12th to 14th September in Bern (details follow).
Subgroups and parties are requested to submit asap the list of participants to DTP7 (number of participants is limited to 40)