## Slide 1: WLTP 6th DHC Meeting
GRPE/WLTP-IG/ DHC subgroup
11~12 January 2011
Palais des Nations, Geneva

## Slide 2
Contents
Current Status
  In-use Data Collection
  Data Analysis Methodology
Open Issues
Next Actions
(ref.) Test Program of Validation 1
Additional Statements
Table of Contents

## Slide 3: 1. Current Status
1. In-use Data Collection
2. Methodology  please refer to WLTP-DHC-06-03e
 | In-use Data | Traffic Statistical Information
China |  | 
EU | Completed (on going for more data acquisition) | 
India | On going (expected to complete by Jan. 2011) | 
Japan | Completed | Completed
Korea | Completed | Completed
USA | Completed | Completed

## Slide 4
2. Open Issues -1
 | Issues | Discussion points | Proposed Actions
1 | Regional Weighting when developing the WLTC | traffic volume same weighting | Wait for initial analysis, then make a decision during 7th DHC meeting
2 | Threshold Speed for L/M/H | according to DHC-06-03 CP’s requirement | 
3 | High Phase Cycle Construction (US&EU versus other regions) | only ONE unified cycle possess TWO types of High phase cycle | Wait for initial analysis, then further discussion is necessary before developing the 1st WLTC
4 | Mode Construction | a) cold start test only b) cold start & hot soak start | After developing the 1st WLTC, further analysis is necessary during the validation 1

## Slide 5
2. Open Issues -2
 | Issues | Discussion points | Proposed Actions
5 | Unique Weighting Factor for L/M/H Phase | harmonized weighting factors permit regional weighting factors | After developing the 1st WLTC, check the representativeness for each region.
6 | Gear Shift Points | fixed points based on vehicle specification others | JARI, JRC and Mr. Steven work together to finalize the method before developing the 1st WLTC.
7 | How to treat the vehicles which are not able to follow the prescribed cycle | continue to drive with wide-open-throttle exempt the H (or M&H) phase(s) others | Develop the proposal during validation 1 tests.

## Slide 6
3. Next Actions up to Validation 2
 | 2011 |  |  |  |  |  |  |  |  | 
 | Jan. | Feb. | Mar. | Apr. | May | Jun. | Jul. | Aug. | Sep. | Oct.
Meetings |  |  |  |  |  |  |  |  |  | 
In-use data collection |  |  |  |  |  |  |  |  |  | 
Develop the harmonized cycle |  |  |  |  |  |  |  |  |  | 
Validation |  |  |  |  |  |  |  |  |  | 
Open Issues |  |  |  |  |  |  |  |  |  | 
DTP Activities |  |  |  |  |  |  |  |  |  | 
The threshold of L/M/H
High phase construction
Detailed plan for validation1
Validation2
Validation1
Introduce
1st WLTC
original
current
Initial
analysis
Develop
1st WLTC
Final
DEADLINE
7th DHC
8th DHC
10th DHC
Modify, if necessary
Detailed plan
for validation2
Introduce
2nd WLTC
preparation
1st draft test procedure
9th DHC
62nd GRPE
1, 2
3, 6
4, 7
5

## Slide 7
4. (ref.) Test Program of Validation 1
Japan plans to evaluate the shaded portions. Any voluntary works are welcome and it’d be appreciated if these work plans are informed to secretary by the middle of February. Detailed plan will be introduced during next (7th) DHC meeting. (expected to be held late February or early March 2011)
 |  | Test Vehicles * |  |  |  | 
 |  | #1 | #2 | #3 | #4 | Unique technologies (e.g. regeneration system, hybrid, PEV)
 | SMOOTH THROTTLE OPERATION |  |  |  |  | 
 | APPROPRIATE SHIFT POINT |  |  |  |  | 
 | CLUTCH OFF POINT |  |  |  |  | 
 | MODE TRACEABILITY |  |  |  |  | 
 | TIRE LOCK, SLIP |  |  |  |  | 
REPEATABILITY ** (including different test drivers) |  |  |  |  |  | 
Request from DTP (e.g. additional pollutants, etc) |  |  |  |  |  | 
DRIVEABILITY
PRACTICABILITY
( MT vehicles only )
* ) vehicles configurations are based on its “power to mass ratio”, “DTC”, “compliance emission level” and so on.
** ) emission level, driving energy index, etc

## Slide 8
Consensus with Indian delegates
Submit the available data by the end of January 2011
Submit the additional data by the middle of April 2011
 Start initial analysis from the middle of April 2011
3. Submit the all data by the end of April 2011
 all data will be reflected for cycle development
4. No more delay will be expected, however,
if it’s the case, accept to move on to data analysis
and cycle development without having all data.
Note)
Data can be submitted whenever the data is available.
5. Additional Statements -1-

## Slide 9
Consensus with Chinese delegates
Inform Chinese decision by 27th January 2011
for the following items.
a) how much data can be collected by the middle of
April 2011 ?
b) is it acceptable for China to move on to data analysis
and the cycle development from the middle of April
2011 with partial data ?
2. It is preferable to submit the data whenever data is available
before the middle of April.
5. Additional Statements -2-