## Tabelle1
| Year/Month | 2012/03 | 2012/06 | 2012/11 | 2013/03 | 2013/06 | 2013/11 | 2014/03 | 2014/06 | 2014/11 | 2015/03 | 2015/06 | 2015/11 | 2016
Item / Decision (d) or Work (w)
SW EU-ETAES (d) |  |  | WP29 |  | SW in UNECE | Pilot Phase** |  |  |  |  | DETA Start officially |  |  | [IWVTA Start]
Steering-Board |  | IG of DETA is active (w) |  | Permanent group (d) | [6 empty] | Steering board in force
Implementing stages |  | TRY-Out active |  | Access-rights and Firstpage (d) |  | TAA optional 1. Systems and parts |  |  |  |  | TAA mandatory 1. Systems and parts |  |  | Approval Authorities 2. IWVTA
Financing * |  | EX-Committee for UN (Staff) | Prepare financing informal doc | WP 29 on Financing scheme | SW-License /Service financing | [5 empty] | Payment start by TAA
Server Hosting |  | TAA-GER |  |  | [UNECE]
Unique Identifier (UI) |  | Format of UI (d) in WP29 | Guideline for drafting UI relevant amendments | Start proposals for different GRs | [6 empty] | [First UI possibility?]
Change of 58-Agreement |  | (WP29)/w + proposals by IG DETA |  |  | Draft in WP29 |  |  | adopted by WP29 |  | Rev3 of 1958 agreement
Change of sep. UN-Regs |  |  |  | Draft proposals in the GRs | [7 empty] | GRs Prop to UN Regs
UN-R0 contribution |  | Proposals to UN R0 in written procedure |  | Draft UN R0 to WP29 | [7 empty] | UN R0 approved by WP29
* Until decision on financing and/or for the Try Out;TAA-GER (KBA) takes care of the available Server
** Pilot Phase for Soft-Ware (SW) seen as the time to upload real approvals