## revised Roadmap20120605
|  |  | 2011 |  | 2012 | [11 empty] | 2013 | [11 empty] | 2014
|  |  | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6
Phase I Work | Meetings |  | 2013 10: 162nd WP.29; 2014 2: 162nd WP.29
Ad-Hoc GRPE
DHC/DTP/VTF
[5 empty] | 63rd GRPE |  |  | DTP/VTF |  | 64th GRPE | [6 empty] | 65th GRPE |  |  |  |  | 66th GRPE | [6 empty] | 67th GRPE
[6 empty] | version 0 |  |  |  | version 0' | [6 empty] | version 1 |  |  | version 2 | [8 empty] | ( modify, if necessary )
| development of gtr Text |  | 2013 9: Submit; 2014 1: Submit formal document
[11 empty] | modify based on Validation2 test | [6 empty] | reflect |  | revise, |  | Final refine |  |  | formal document
| Overall structure | Drafting manager | 2013 9: final gtr
(DHC,DTP)
| Technical report | Drafting manager | 2012 6: version 1; 2012 11: version 2 (informal doc.); 2013 4: Draft technical report (informal doc.)
(DHC,DTP)
Sub Group Activities
| DHC |  | 2012 12: Completed
| Development of harmonized cycle |  | 2012 1: Distribute WLTC; 2012 6: Cycle modification,; 2012 10: final check
[5 empty] | for Validation2 |  |  |  |  | if necessary
Validation 1
DTP
|  | ICE | 2012 12: fix major; 2013 4: eliminate all open issues
|  | E-lab. | 2012 12: open issues
PN/PM
|  | AP | 2012 6: Feedback
Fuel
Feedback
VTF | bar: 2012 4 to 2013 1
Validation 2 | bar: 2012 4 to 2013 1
[9 empty] | test execution |  |  |  |  | analysis
| report |  | 2013 1: final report
interim report
Road-Load Determination | bar: 2012 9 to 2013 1
| report |  | 2012 12: final report
Confirmation test | bar: 2012 8 to 2013 5
report | bar: 2012 8 to 2013 5
final report
Round Robin tests | bar: 2012 8 to 2013 1
report | bar: 2012 8 to 2013 1
[20 empty] | interim report @GRPE |  |  |  |  | final report @GRPE
Phase II & III | bar: 2012 7 to 2013 1
re-consider work elements
[11 empty] | during Phase II&III | [5 empty] | Review Phase II&III Roadmap |  |  |  |  | Agreement of Phase II&III Roadmap | [7 empty] | Start Phase II Work
Informal document
(draft gtr)
Informal document
(nearly finalized draft gtr)
( gtr version1 base)
( gtr version1 base)
(include low powered vehicle cycle)
(include low powered vehicle cycle)
review & fix
testing element
review & fix
testing element
preparation
preparation

## revised Roadmap
|  |  | 2011 |  | 2012 | [11 empty] | 2013 | [11 empty] | 2014
|  |  | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6
Phase I Work | Meetings |  | 2013 10: 162nd WP.29; 2014 2: 162nd WP.29
Ad-Hoc GRPE
[5 empty] | 63rd GRPE |  |  | DTP/VTF |  | 64th GRPE |  |  | DTP/VTF |  |  |  | 65th GRPE |  |  |  |  | 66th GRPE | [6 empty] | 67th GRPE
[6 empty] | version 1 |  |  |  | version 2 | [6 empty] | version 3 |  |  | version 4 | [8 empty] | ( modify, if necessary )
| development of gtr Text |  | 2013 9: Submit; 2014 1: Submit formal document
[11 empty] | modify based on Confirmation test | [6 empty] | reflect |  | revise, |  | Final refine |  |  | formal document
| Overall structure | Drafting manager | 2013 9: final gtr
(DHC,DTP)
| Technical report | Drafting manager | 2012 4: version 1; 2012 6: version 2; 2012 11: version 3 (informal doc.); 2013 4: Draft technical report (infromal doc.)
(DHC,DTP)
Sub Group Activities
DHC
| Development of harmonized cycle |  | 2012 1: Distribute WLTC; 2012 6: Distribute revised WLTC; 2013 1: Distribute revised WLTC for Round-Robin
[5 empty] | for Validation2 |  |  |  |  | for confimration test | [6 empty] | Completed
Validation 1
DTP
ICE
E-lab.
PN/PM
|  | AP | 2012 6: Feadback
Fuel
Feadback
VTF
Validation 2
report
[11 empty] | interim report |  | final report
Confirmation test
report
final report
| Round Robin tests | OICA
[16 empty] | International | ( GOLDEN vehicle @ GOLDEN laboratory in each region )
[16 empty] | Regional | ( semi-GOLDEN vehicle in each region )
report
[20 empty] | interim report @GRPE |  |  |  |  | final report @GRPE
Phase II & III
[11 empty] | Review WLTP Phase II work | [5 empty] | Review Phase II&III Roadmap |  |  |  |  | Agreement of Phase II&III Roadmap | [7 empty] | Start Phase II Work
Informal document
(draft gtr)
Informal document
(nearly finalised draft gtr)
( gtr version2 base)
( gtr version3 base)
(include low powered vehicle cycle)
(include low powered vehicle cycle)
Tentative Schedule
VTF provide the specific time frame of Validation2 and Confirmation test

## Organization
WLTP Organization (as of Jan. 2012)
Responsibilities / Functions
|  | Steering Group |  | Supervise and support all WLTP activities and all sub groups permanently
|  | Sponser CPs (EU/JPN) |  | Preparation of WLTP documents, then up to UNECE website
|  | India Representative |  | (non specific DHC or DTP documents)
|  | GRPE Chair |  | Clarification of responsibilities
|  | WLTP Secretary |  | Organisation of the WLTP project process
|  | OICA Representative |  | (timing, information flow, coordination)
DTP |  | DTP Chair | 5 technical sub-group | Develop world-wide harmonized test procedure
|  |  | (ICE, PN/PM, AP | Develop gtr text
|  |  | E-Lab., Fuel) | Develop the content of the Technical report
OICA
Responsible for Round-Robin test
(provide test vehicles and vehicle transportation fee)
| VTF | VTF Chair |  | Develop ToR and provide the technical guidance
Supervise and support validation2/confirmation test excusion
Develop ToR for road-load determination
| gtr Drafting | Drafting Manager |  | Develop a rules of procedure and gtr structure
Supervise and support gtr text development
Develop the format of the Technical report
DHC |  | DHC Chair |  | Develop world-wide harmonised test cycle
Supervise and support validation1 test excusion
Develop gtr text
Develop the content of the Technical report

## Organization(after val1)
Proposed WLTP Organization (after completion of validation1)
Responsibilities / Functions
WLTP informal group |  |  | Supervise and manage all WLTP activities and all sub groups permanently
Preparation of WLTP documents, then up to UNECE website
Clarification of responsibilities
Organisation of the WLTP project process
(timing, information flow, coordination)
| Combined DTP/DHC | Remaining DHC function | Modify test cycle, if necesarry
|  | 5 technical sub-group | Develop world-wide harmonized test procedure
|  | (ICE, PN/PM, AP | Develop gtr text
|  | E-Lab., Fuel) | Develop the content of the Technical report
|  | VTF | Develop ToR and provide the technical guidance
Supervise and support validation2/confirmation test excusion
Develop ToR for road-load determination
|  | gtr Drafting | Develop a rules of procedure and gtr structure
Supervise and support gtr text development
Develop the format of the Technical report
OICA
Responsible for Round-Robin test
(provide test vehicles and vehicle transportation fee)
should be combined to one(1) group
OR

## Meeting Schedule in 2012
Tentative Meeting Schedule in 2012
week | date | DHC | DTP |  | VTF | Drafting Manager | milestones
DTP sub-groups
1 | 2~6 Jan. |  |  | each sub-group chair will announce the meeting date based on progress
2 | 9~13 Jan. | 11th @ Geneva | 8th @ Geneva |  | 2nd @ Geneva | gtr structure | Update the current status from each group
3 | 16~20 Jan.
4 | 23~27 Jan.
5 | 30~3 Feb.
6 | 6~10 Feb. | 12th @ Web. |  |  | 3rd @ Web. |  | Start validation2 test DHC : Provide the revised test cycle based on validation1b VTF : Provide the technical guideline
7 | 13~17 Feb.
8 | 20~24 Feb.
9 | 27~2 Mar.
10 | 5~9 Mar.
11 | 12~16 Mar.
12 | 19~23 Mar.
13 | 26~30 Mar.
14 | 2~6 Apr.
15 | 9~13 Apr.
16 | 16~20 Apr. |  | 9th @ Bern |  | 4th @ Bern | gtr ver.1 Technical Report ver.1 | DTP : Review the progress on open issues and reflect the closed issues to gtr ver.1 VTF : Progress report on validation2 and preparation for confirmation test Drafting : Review gtr/Tecnincal report ver.1
17 | 23~27 Apr.
18 | 30~4 May.
19 | 7~11 May.
20 | 14~18 May.
21 | 21~25 May.
22 | 28~1 Jun.
23 | 4~8 Jun. | 13th @ Geneva | 10th @ Geneva |  | 5th @ Geneva | gtr ver.2 Technical Report ver.2 | Start confirmation test based on gtr ver.2 DTP : Reflect the closed issues to gtr ver.2 and make it clear to be resolved during the confirmation test VTF : Report validation2 test results and provide the technical guideline for confirmation test Drafting : Review gtr/Tecnincal report ver.2
24 | 11~15 Jun.
25 | 18~22 Jun.
26 | 25~29 Jun.
27 | 2~6 Jul.
28 | 9~13 Jul.
29 | 16~20 Jul.
30 | 23~27 Jul.
31 | 30~3 Aug.
32 | 6~10 Aug.
33 | 13~17 Aug.
34 | 20~24 Aug.
35 | 27~31 Aug.
36 | 3~7 Sep. |  | 11th @ tdb (either week) |  | 6th @ tbd (either week) |  | DTP : Review the progress on open issues VTF : Progress report on confirmation test OICA : Prepare round-robin test
37 | 10~14 Sep.
38 | 17~21 Sep.
39 | 24~28 Sep.
40 | 1~5 Oct.
41 | 8~12 Oct.
42 | 15~19 Oct.
43 | 22~26 Oct.
44 | 29~2 Nov.
45 | 5~9 Nov.
46 | 12~16 Nov.
47 | 19~23 Nov.
48 | 26~30 Nov. |  |  |  |  | gtr/Technical report ver.3 @ tbd (either week) | Reflect validation/confirmation test result on gtr Prepare informal document of gtr text (close to final version)/Technical report
49 | 3~7 Dec.
50 | 10~14 Dec.
51 | 17~21 Dec.
52 | 24~28 Dec.