## Schedule IG Plastic Glazing
Draft Schedule of Informal Group on Plastic Glazing |  |  |  | Apr. 09, 2013
Rev. 3
|  |  | Year | 2010 |  |  | 2011 | [11 empty] | 2012 | [11 empty] | 2013
|  |  |  | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  |  | WP.29 | 2010 11: 152; 2011 3: 153; 2011 6: 154; 2011 11: 155; 2012 3: 156; 2012 6: 157; 2012 11: 158; 2013 3: 159; 2013 6: 160; 2013 11: 161
|  |  | GRSG | 2010 10: 99; 2011 4: 100; 2011 10: 101; 2012 4: 102; 2012 10: 103; 2013 4: 104; 2013 10: 105
General Schedule |  |  |  | 2010 12: ToR Proposal; 2011 2: ToR approval; 2011 4: PR #1; 2011 12: PR #2; 2012 5: PR #3; 2012 12: I/D Final PR; 2013 5: GRSP approval; 2013 11: WP29 voting
Informal face-to-face meeting for research/validation and development |  |  |  | 2011 1: #1 BASt; 2011 4: #2 UN; 2011 6: #3 ESV; 2011 9: #4 Japan; 2011 12: #5 UN; 2012 5: #6 UN; 2012 9: #7; 2012 12: #8 UN; 2013 5: #9 UN; 2013 7: #10; 2013 11: #11 UN
Development supported by Web meetings to develop regulatory text | bar: 2012 6 to 2013 5
General Schedule |  |  |  | 2010 10: TOR Proposal; 2011 3: ToR Approval; 2011 4: 1st Progress Report; 2011 10: 2nd Progress Report; 2012 4: 3rd Progress Report; 2012 10: Report and Draft Proposal; 2013 4: Report and Draft Proposal; 2013 10: Report
Informal face-to-face meeting |  |  |  | 2011 1: 1st Meeting; 2011 6: 2nd Meeting; 2011 11: 3rd Meeting; 2012 1: 4th Meeting; 2012 9: 5th Meeting; 2013 1: 6th Meeting; 2013 6: 7th Meeting; 2013 11: 8th Meeting
Phase 1 | Development of ToRs | bar: 2010 10 to 2011 1
Draft Working Paper on Plastic Glazing | bar: 2010 10 to 2011 3
Discussion of Work Items | bar: 2010 10 to 2011 6
Phase 2 | Exchange of information based on Research Activities | UV stability (radiation test) | bar: 2011 5 to 2012 9
Weathering test | bar: 2011 5 to 2012 9
Abrasion test | bar: 2011 5 to 2013 12
Chemical test | bar: 2011 5 to 2012 9
Durability test | bar: 2011 5 to 2012 9
Vulnerable road users | bar: 2011 1 to 2011 8
Phase 3 | Decision on Test Procedures | bar: 2011 11 to 2013 8
Decision on Requirements and Limits | bar: 2011 11 to 2013 12
Preparation of Draft Amendment Text | bar: 2012 1 to 2013 12
|  |  | Year | 2010 10: 2014; 2011 10: 2015
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 12
|  |  | WP.29 | 2014 3: 162; 2014 6: 163; 2014 11: 164; 2015 3: 162
|  |  | GRSG | 2014 4: 106; 2014 10: 107; 2015 4: 106
General Schedule | bar: 2014 4; 2014 10; 2015 3
Informal face-to-face meeting | bar: 2014 2; 2014 5
Phase 1 | Development of ToRs
Draft Working Paper on Plastic Glazing
Discussion of Work Items
Phase 2 | Exchange of information based on Research Activities | UV stability (radiation test)
Weathering test
Abrasion test | bar: 2014 1 to 2014 2
Chemical test
Durability test
Vulnerable road users
Phase 3 | Decision on Test Procedures
Decision on Requirements and Limits | bar: 2014 1 to 2014 2
Preparation of Draft Amendment Text | bar: 2014 1 to 2014 7