**Economic Commission for Europe**

Meeting of the Parties to the Convention
on Environmental Impact Assessment
in a Transboundary Context

**Eighth session**

Meeting of the Parties to the Convention
on Environmental Impact Assessment in
a Transboundary Context serving as the
Meeting of the Parties to the Protocol on
Strategic Environmental Assessment

**Fourth session**

Vilnius, 8–11 December 2020

Item 4 of the provisional agenda

**Review of the workplan**

|  |  |  |
| --- | --- | --- |
|  |  |  ECE/MP.EIA/2020/INF.5 Original: English 12 October 2020 |

**Workplan implementation status**

This note by the secretariat provides for information of the Meetings of the Parties an informal assessment of the implementation status of activities in the 2017–2020 workplan of the Convention and its Protocol (adopted through decision VII/3–III/3). The activities for which funding is available or that do not require funding are listed in annex I, and the waitlisted activities in annex II to the note. As resources for the waitlisted activities became available, their implementation was monitored as part of the workplan (they were moved up to annex I).

Annex III to the note lists additional activities, with funding, that were not originally in the workplan but that were subsequently requested by countries and relate to the workplan.
To facilitate the review of the workplan and its annexes, the following colours are used to indicate their degree of implementation.

|  |  |  |  |
| --- | --- | --- | --- |
| *Degree of implementation* | *Workplan activities/sub-activities* | *Activities awaiting funding/confirmation*  | *Additional activities* |
| Completed | 40 (74%) |  | 10 (56%) |
| Ongoing/Firm arrangements with funding. | 8 (15%)  |  | 5 (28%) |
| To be done (in kind by Parties or the secretariat). | 0 |  |  |
| Initial arrangements/funding identified. | 0 |  | 2 (11%) |
| Cancelled/no funding/no arrangements.  | 6 (11%) |  | 1 (5%) |
| **Total** | **54** | **15** | **18** |

 Annex I

 Workplan for the implementation of the Convention and its Protocol for the period 2017–2020

| *Activity/sub-activities* | *Organizational arrangements/lead countries* | *Time schedule* | *Budget* | *Status* |
| --- | --- | --- | --- | --- |
|  |  |  |  |  |
| **I. Compliance with and implementation of the Convention and the Protocol** |  |  | Most items included in Implementation Committee and secretariat costs. Exceptions are identified below. |  |
| I.1. Consideration by the Implementation Committee of compliance submissions and Committee initiatives. |  Implementation Committee, with the support of the secretariat. | 2017–2020, presented to MOP8 and MOP/MOP4 | May require funding for translation of submissions ($10,000). | Completed. |
| I.2. Report on the Committee’s activities to MOP8 and MOP/MOP4. | Implementation Committee, with the support of the secretariat. | 2017–2020, presented to MOP8 and MOP/MOP4 | — | Completed. |
| I.3. If necessary, review of the Committee’s structure and functions and operating rules. | Implementation Committee, with the support of the secretariat. | 2017–2020, presented to MOP8 and MOP/MOP4 | — |  Completed (one amendment is proposed) |
| I.4. Examination of the outcome of the fifth review of implementation of the Convention and the second review of implementation of the Protocol. | Implementation Committee, with the support of the secretariat. | By the end of 2017 | — | Completed with two cases to be continued in the next intersessional period due to lack of a response form two Parties (North Macedonia – regarding the Convention and Serbia – regarding the Protocol) |
| I.5. Distribution to Parties of the questionnaires for reporting on implementation of the Convention and the Protocol in 2016–2018. | Secretariat and Parties to the Convention and the Protocol. | Questionnaires issued by end of October 2018 Return of questionnaires by end of March 2019  | — | Completed by the secretariat: both questionnaires distributed on 30 October 2018.Completed: Reporting by Parties completed.  |
| I.6. Preparation of draft reviews of implementation of the Convention and the Protocol. | Secretariat. | Presentation of the draft reviews to the Committee and the Working Group in autumn 2019 and to MOP8 and MOP/MOP4 | Requires external consultants and translation of national reports ($25,000 is required from the core budget).*a* | Completed Draft reviews prepared and discussed by the Working Group in November 2019 and finalized for MOP8 and MOP/MOP4 based on comments received, and after a review by the Bureau/Working Group. |
| I.7. Pre-accession technical legislative advice to a country or countries wishing to join the Protocol and/or the Convention to review national legislation for implementation of the Protocol and/or the Convention and to draft primary or secondary legislation or propose amendments. | Lead/requesting country:(a) Kazakhstan: advice on drafting legislation on SEA to promote ratification of the Protocol and on transboundary EIA to promote the implementation of the Convention*(Moved from annex II)*  | To be defined by the requesting countries. | Funding from the European Union, *b* Germany, Switzerland, and OSCE. |  (a) Completed, with support from the secretariat. Draft recommendations on SEA and EIA procedures, including amendments to the law (Environmental Code) of Kazakhstan, draft secondary legislation on SEA discussed at four consultation meetings in Astana (16-17 November 2017; 15-16 February; 25-26 April; and 5 September 2018). Final consultation held on 14 November 2018. (Funding from EU) (Further support provided in Sept. 2020, see annex III).  |
| (b) Tajikistan: review of national SEA legislation; support in legal drafting; awareness-raising event to promote adoption of the amended law; | (b) Completed with support from the secretariat. Review of SEA related legislation in Tajikistan finalized in February 2019. An awareness-raising workshop held on 23 November 2018; a second workshop on the development of national SEA system held on 18 January 2019. (Funding from Germany) |
|  | (c) Uzbekistan: review of national SEA; two to three national seminars on application of the Protocol. |  |  | (c) Completed with support from the secretariat. SEA legislative review finalized in Uzbekistan in December 2018. At the Government’s request, based on the reviews’ recommendations, a concept note on SEA legislative reform, and draft amendments to legislation (Law on Ecological Expertise) developed in December 2018. Activity supported by several events: an awareness raising workshop (Tashkent, 27 August 2018), a meeting of a working group on legal drafting (Tashkent, 24-25 October 2018), a capacity building workshop (Tashkent, 23 January 2019). [Further legal drafting support on EIA/ SEA requested (see annex III for details).] |
|  | (d) Kyrgyzstan (tbc): review of national SEA legislation; two awareness-raising events to promote SEA. |  |  | (d) Cancelled. Kyrgyzstan has not confirmed its request/commitment. |
| I.8. Collection of findings and opinions from the Committee regarding the Convention and the Protocol, posted on the website. | Secretariat. | Annual updates | — | Completed. |
| I.9. Draft terms of reference for possible guidance on addressing the applicability of the Convention with regard to decisions on the lifetime extension of nuclear power plants, involving a workshop to discuss and recommend their adoption by the Working Group on EIA and SEA.  | Lead countries: Germany and the United Kingdom of Great Britain and Northern IrelandThe terms of reference developed by an ad hoc working group including, among others, the following other States Parties (list updated after IS-MOP): Armenia, Austria, Belarus, Belgium, Bulgaria, Canada, Czechia, France, Finland, Greece, Italy, Luxembourg, the Netherlands, Norway, Poland, Portugal, Slovenia, Slovakia, Spain, Sweden, Switzerland, Ukraine, and the European Commission, serving as a secretariat to the group. (The ad hoc group might subsequently be extended to include international organizations and NGOs, as decided by the Working Group on EIA and SEA).The workshop organized by the ad hoc working group, with the participation, among others, of the Implementation Committee, civil society and, possibly, IAEA and OECD/NEA. | First meeting of the ad hoc group in the fourth quarter of 2017, to be followed by at least one other meeting prior to the seventh meeting of the Working Group on EIA and SEA (date to be specified).Terms of reference and the possible extended scope of the ad hoc working group to be agreed by the Working Group on EIA and SEA in May 2018.  | — | Terms of reference prepared and adopted by the Working Group in May 2018 - work ongoing for drafting guidance (see annex III below). To prepare the ToR, the ad hoc group met twice (Luxembourg, 27-28 December 2017 and 20-21 February 2018) and also organized a workshop during WG7. The Netherlands funded additional Russian interpretation for the workshop.  |
| I.10 Finalization of the development and update of the Guidelines on EIA in a Transboundary Context for Central Asian Countries: | Central Asian countries with the support of external consultants and the secretariat. | By 2020 | Funding from Switzerland. | Completed. The Revised Guidelines prepared and amended further to comments by Working Group in May 2018. Endorsed by IS-MOP by decision IS/3 in February 2019. Published in English and Russian in October 2019.  |
| (a) One subregional meeting for Central Asian Countries (to be organized back to back with the subregional conference in Ukraine  |  |  |  | Completed. Reported under item II.C (b)) on subregional activities.  |
| (b) Reviews of national legislation with regard to compliance with the provisions of the Convention and the development of recommendations (to enhance part III of the draft Guidelines). |  | By summer 2018 | Costs: Approximately $7,000–$10,000 per country for consultancy costs. |  |
| (i) Kazakhstan |  |  | (i) Completed. EIA review and recommendations prepared for Kazakhstan (March 2018); |
| (ii) Uzbekistan |  |  | (ii) Completed. EIA review and recommendations prepared (December 2018); a concept note on EIA legislative reform, and first draft amendments to primary legislation (Law on Ecological Expertise) developed further to the review results in December 2018 |
| (iii) Tajikistan |  |  | (iii) Completed. EIA review for Tajikistan finalized in February 2019); |
|  |  (iv) Turkmenistan |  |  | (iv) To be confirmed for Turkmenistan (idem for the funding) |
| (c) National awareness-raising events to support the updating of the Guidelines on EIA in a Transboundary Context for Central Asian Countries and to promote its application.*(Moved up from annex II)* | Lead/target countries: Undertaken by external consultant(s), with the support of a national coordinator and the secretariat | 2017–2020 | Requires donor funding ($7,000 per event).Event in Kazakhstan funded by EU, events in Tajikistan and Uzbekistan by Switzerland |  |
|  (i) Kazakhstan, |  |  | (i) Completed for Kazakhstan (Astana, 15-16 February 2018) back to back with the working group meeting on legal drafting. |
| (ii) Tajikistan,  |  |  | (ii) Completed for Tajikistan (Dushanbe, 22 November 2018). |
| (iii) Uzbekistan.  |  |  | (iii) Completed for Uzbekistan (Tashkent, 26 August 2018) |
| (iv) Turkmenistan  |  |  | (iv) No funding/ cancelled |
| I.11. Technical legislative advice to Parties to the Convention and/or the Protocol requesting assistance (review of primary or secondary legislation; proposals for amendments).*(Moved up from annex II)* | Lead/requesting country:a) Azerbaijan: drafting of secondary legislation; b) Belarus: review of current primary and secondary legislation on SEA and EIA;c) Republic of Moldova: review of primary and secondary legislation and proposals for amendments. |  | 2019-2020  | Funding from EU4Environment confirmed: (a) Completed: support for finalizing the secondary legislation provided including a review of the draft legislation and a virtual roundtable on secondary legislation on 18 August 2020 (b) Ongoing: support for reviewing primary and secondary legislation (Sept 2020 – Feb 2021)(c) Ongoing: support for reviewing legislation finalized in July 2020 and developing proposals for amendments is being initiated (in Sept. 2020) (expected completion spring 2021).  |
| I.12. After the adoption of national law by Georgia, pilot on the application of transboundary EIA between Armenia and Georgia to test their respective laws and improve transboundary procedures.*(Moved up from annex II)* | Lead/requesting country: Armenia, in cooperation with Georgia.Undertaken by external consultant(s), with the support of the secretariat. |  | Funding obtained. (Requires around $100,000). | Transboundary EIA pilot no longer planned: Armenia and Georgia chose national SEA pilots under EU4Environment. |
| I.4. Elaborate a long-term strategy and action plan for the future of the Convention and the Protocol (see draft decision VII/7–III/6).*(Moved up from annex II)* | To be carried out by lead countries and organizations, with support from a consultant and the secretariat. To be adopted by the Meetings of the Parties. | 2017–2020 | Requires in-kind contributions or a consultant for drafting (approximately $15,000). | Completed (draft submitted for consideration of the MOPs). 3 informal meetings of volunteering Parties held to draft a strategy with support from the secretariat. Based on meetings co-chaired by Austria and the Netherlands (London, 1 October 2018 and Rotterdam, 7 October 2019), a draft strategy submitted to WG8 in Nov 2019. A revised draft prepared based on a meeting co-chaired by the Netherlands and Poland (Warsaw, 23-24 January 2020) considered by the Bureau and by WG9 in August 2020.  |
| **II. Subregional cooperation and capacity-building to strengthen contacts between the Parties and others, including States outside the ECE region** |  |  |  |  |
| **II.A. Baltic Sea subregion**  |  |  |  |  |
| Two meetings on topics to be identified by the lead countries.  | Lead countries: Denmark, Finland and Sweden.  | (a) Autumn 2018 (possibly on a ship between Finland and Sweden); (b) Autumn/ winter 2019 in Denmark. | In kind. | Completed (by the MOPs, in October). The two events were merged into one subregional cooperation workshop for the Baltic Sea, hosted by Denmark (Copenhagen on 27-28 October 2020), involving cooperation with Finland and Sweden.  |
| **II.B. South-Eastern Europe subregion** |  |  |  |  |
| A dedicated session on implementation of the Convention, the Protocol and the Bucharest Agreement in the subregion. | Lead countries/organizations: Croatia, Romania and Slovenia and the secretariat, held under the auspices of a regional conference on EIA hosted by Croatia.  | 14 September 2017, in Vodice, Croatia | In kind (but funding required for travel of additional experts/participants) | Completed in September 2017. |
| **II.C. Eastern Europe, the Caucasus and Central Asia, and beyond**Subregional coordination and experience-sharing events to share successes, challenges, solutions and experiences as well as the results of capacity-building activities on SEA and EIA, followed by the dissemination of seminar results in all countries of Eastern Europe, the Caucasus and Central Asia, including to the public and NGOs: | Lead/host countries, with support from the secretariat and from a local counterpart/NGO for logistical arrangements.  |  |  |  |
| (a) Subregional workshop building on the updated Guidelines on EIA in a Transboundary Context for Central Asian Countries; | Lead/host country: Kyrgyzstan. Participation by all countries in Central Asia. Could be extended to countries outside ECE, e.g., in South-East Asia. (Organized back to back to the subregional coordination and experience-sharing event scheduled to take place in Ukraine in late 2017). | Autumn 2017  | Partial funding available (reallocation of funds Switzerland provided in 2011 for legislative support to Uzbekistan); if extended beyond ECE, further donor funding required.  | Completed. Held in Kyiv, 2 and 3 November 2017. (see item I.10 (a)) |
| (b) Seminar on lessons learned from capacity-building activities in 2014–2017, including SEA pilot projects in Armenia, Azerbaijan, Belarus, Georgia, the Republic of Moldova and Ukraine; and a subregional training-of-trainers event on SEA. | Lead/host country: Ukraine. Participation by all countries in Eastern Europe and the Caucasus.  | October–November 2017 (exact dates tbc)  | Funding from the European Union (EaP-GREEN).*d* | Completed. Held in Kyiv, 31 October–2 November 2017). |
| II.C.4. Promotion of principles of the Convention and the Protocol in Central Asia and beyond in the context of the recent economic developments in Asia: | Lead/target countries: Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan and Uzbekistan and other countries. |  |  |  |
| Subregional seminar to promote the application of the Guidelines on transboundary EIA for Central Asian countries (among high-level officials) at the Central Asian International Environmental Forum in Uzbekistan, possibly in the context of the “one belt one road initiative”.*(Moved from annex II)* | To organized by CAREC and Uzbekistan. | Tentatively in summer 2018.  | Requires funding: ($7,000-10,000)  | Completed. Held in Tashkent on 4 June 2018 with the funding from Switzerland, EU and UN regular programme for technical cooperation. |
| II.C.5. Subregional conference with training of trainers on the application of SEA to climate change mitigation, to be followed by national training sessions and supplemented by the preparation of guidance.*(Moved from annex II)* | To be hosted by a lead country and contributed to by all participants. (Could be extended to all Central Asian countries (and beyond)).To be carried out by external consultants, with support from a local counterpart and the secretariat. | May/June 2020 (tbc) | Costs: Subregional conference for up to 50 participants: $40,000–$80,000 (depending on the duration). Staff costs for project management: P-3, $15,000 per month and G-4, $8,500 per month. Requires donor funding.Funding is obtained. | A subregional conference for six Eastern Europe countries funded through EU4Environment held on 26-27 October 2020 as a virtual event.  |
| **III. Exchange of good practices**Workshops or half-day seminars within meetings of the Working Group or the Meetings of the Parties on: | To be organized by a lead country(ies) with support from the secretariat. | 2017–2020 | Costs (e.g., for speakers, provision and translation of materials) to be covered in kind by lead countries, to the extent possible (approximately $10,000 per seminar). (Travel costs for countries eligible for financial support and non-ECE countries should be covered from the budget.) |  |
| (a) Seminar on improving intersectoral cooperation and institutional arrangements for the application of the Protocol on SEA and the Convention; | Secretariat with inputs from volunteering delegates and with the possible participation of WHO. To be held in the framework of a meeting of the Working Group on EIA and SEA. | 2019 | In kind. | Completed. The secretariat organized a workshop on the assessment of health impacts and health sector involvement in SEA during the Working Group’s 8th meeting in November 2019, in cooperation with WHO and EIB, and with support from consultants. Selected good practice was presented by Czechia, Estonia, the Netherlands, and Wales (UK) (and reflected in the draft guidance on health submitted to WG9 ). |
| (b) Synergies between transboundary EIA and SEA and UNCLOS, arts. 204-206*(moved from annex II)* | Lead organization: European Commission. | 2019-2020 | In kind. | Cancelled by the European Commission. |
| (c) Other workshops (tbc) |  |  |  |  |
| **IV. Promoting ratification and application of the Protocol on SEA and/or the Convention** IV.1. Workshops, including training, on the application of the Protocol for countries in the ECE region and other Parties to the Protocol, in particular countries of Eastern and South-Eastern Europe, the Caucasus and Central Asia: | Lead countries with the support of the secretariat and external consultant(s) and national counterparts | 2017–2020 |  |  |
| One national training event  | Kazakhstan. | 2015–2017 | European Union funding for Kazakhstan.*b* with co-funding from OSCE | Completed. Training workshops in Astana within SEA pilot (see IV.4 below) Part 1: on scoping and baseline analysis (8–9 November 2017); Part 2. on impact assessment and SEA report (5 March 2018). Final event on 14 November 2018.  |
| IV.2. National guidance documents on SEA. | Lead country: Kazakhstan | 2017–2018 | Funding from the European Union for Kazakhstan.*b*  | Cancelled - funds reallocated for more extensive legal assistance requested by Kazakhstan. (see activity I.7. (a) above). |
| IV.3. Preparation of two-page informal pamphlets or “FasTips” on key issues in SEA practice on topics to be suggested (e.g., SEA for water management plans or the waste management sector; analytical methods used in SEA; and monitoring) and on the Convention and the Protocol. | Lead organization: IAIA, with the support of WHO, SEA and health experts, and from the secretariat for the dedicated “FasTips” on the Convention and the Protocol. | 2017-2020 | In kind. Translation of (some five) relevant “FasTips” into Russian funded by WWF Russia. | Completed. The secretariat prepared the draft Convention and Protocol “FasTips” , revised them based on Working Group’s comments at its 8th meeting ( Nov. 2019), and submitted them to IAIA. IAIA approved the publishing of the Convention FasTips with a reference added to the Protocol (in Eng, Fr and Ru). The Protocol FasTip not published as found too similar and procedural/legalistic.Completed: Six “FasTips” translated into Russian with EU (EaP GREEN) funding (see: <http://www.iaia.org/translated-documents.php>.Additional work by WWF/Russia to translate several “FasTips” |
| IV.4. Pilot SEA in Kazakhstan, involving the following activities: a) Two workshops for scoping and the analysis of the baseline, impact assessment, development of mitigation measures and development of recommendations; (b) Two public consultation events; (c) Preparation of the SEA report. | Lead country: Kazakhstan as the lead/target country, with the support of an external consultant, national experts and the secretariat, and in collaboration with partner organizations, as relevant. |  | Likely funding from the European Union*b*Costs: for the pilots ($80,000-$100,000) and for staff costs of a project manager and support personnel, P-3 ($15,000 per month) and G-4 ($8,500 per month). | Completed. Pilot launched in November 2017 (see item IV.1. for related training events).The scoping report finalized and submitted to the Ministry of Energy at the end of March 2018. The environmental report finalised in November 2018, discussed with the national stakeholders on 14 November 2018 and submitted to the Ministry of Energy in December 2018. |
| IV.5. Preparation of fact sheets on the application of the Protocol. | Lead countries: Germany and other Parties. (All Parties invited to propose fact sheets. The Party preparing the fact sheet will be responsible for its layout.) | 2017–2020 | In kind. | Issued by Germany in January 2018 and presented at the meeting of the Working Group in May 2018. Ongoing for other Parties. |
| IV.6. Development of country- and sector-specific guidance for the assessment of potential health impacts of plans and programmes and for the involvement of health authorities, building on the chapter on health in the SEA Resource Manual. (Could be linked with a possible subregional workshop.)*(Moved from annex II)* | Undertaken by external consultant(s), with the support of the secretariat and WHO.  |  | EIB funding. (Beneficiary countries to reconfirm their needs.)  | Ongoing (forwarded by the WG9 to the next period.) Based on ToR agreed by WG7 in May 2018 and with funding from EIB, draft prepared by two consultants in consultation with the secretariat, WHO and EIB. Draft revised based on comments by EU at Working Group’s 8th meeting ( Nov. 2019) and inputs from a task force (Austria, Finland, Ireland, Slovenia) and the Bureau. Revised draft submitted for agreement by the Working Group (August 2020) prior to submission to MOP/MOP4WG9 decided not to forward to MOP/MOP but mandated further work by a task force of volunteering Parties and stakeholders (EIB funding no longer available). |
| IV.3. Workshops for national and local sectoral authorities, as well as environmental and health authorities, including training, on the application of the Protocol for countries in the ECE region and beyond and the application of SEA for integrating climate change adaptation and mitigation measures into plans or programmes.*(Moved from annex II)* | To be carried out in cooperation with the lead/target countries, e.g., Armenia, Azerbaijan, Belarus, Georgia, the Republic of Moldova and Ukraine, with support from an external consultant and the secretariat. | 2017–2020 | Requires donor funding ($10,000 for two-day workshop) and in-kind contributions.Funding is obtained. | (a) Georgia. Completed.One training workshop (SEA for municipal spatial plans) held in Georgia with funding from Czechia and EU4Environment on 16-17 May 2019 (b) Georgia. Completed.The second training workshop in Georgia (SEA for municipal spatial plans) organized on 19-20 September 2019 with funding from Czechia and EU4Environment. (c) Ukraine. Firm funding from EU4Environment. One training workshop in Ukraine (SEA procedures) to be completed till the end of 2020. (d) Republic of Moldova. One awareness raising workshop on SEA application completed in Moldova on 1 November 2019 with EU4Environment funding.(e) Republic of Moldova. One training workshop (on quality of SEA and EIA documentation). Completed as a virtual event (December 2020) with EU4Environment funding(f) Belarus. Awareness raising workshop on SEA completed (in December 2020) with EU4Environment funding. (g) Georgia. Completed (as a virtual event in December 2020) with EU4Environment funding. by ne training workshop in Georgia is planned  |
|  |  |  |  |  |
|  |  |  |  |  |
| IV.4. Pilot SEAs in selected countries, in selected sectors, involving the following activities: (a) Two to three workshops for scoping and the analysis of the baseline impact assessment and the development of mitigation measures and recommendations; (b) Two to three public consultation events; (c) Preparation of the SEA report and training on its quality control. *(Moved from annex II)* | Lead/target countries and selected sectors (based on requests by the countries): (a) Armenia (spatial planning); (b) Azerbaijan (water management tbc)(c) Belarus (sector tbc)(d) Georgia (sector tbc); (e) Republic of Moldova (transboundary EIA or SEA); (f) Ukraine (renewable energy tbc); In collaboration with the support of an external consultant, national experts and the secretariat, and partner organizations, as relevant.  | 2019-2020 (2021-2022) | Requires funding for pilot ($80,000-$100,000) and for staff costs of project manager and support personnel, P-3 ($15,000 per month) and G-4 ($8,500 per month). | Pilot SEAs in two countries will be funded by EU4Environment and completed in the next period. 2 pilots (in Armenia and Azerbaijan) planned to start in late 2020. To be completed in the next period. |
| IV.5. National guidance documents on the implementation of SEA.*(Moved from annex II)* | Lead/target country to be identified.Armenia Azerbaijan BelarusGeorgiaRepublic of Moldova Ukraine  | 2020 (2021-22) | Requires funding ($20,000–$40,000). | Ongoing. EU4Environment funding confirmed for Armenia, Azerbaijan, Belarus, Georgia, Republic of Moldova, Ukraine for the preparation of sector or issue specific guidelines on SEA to complement existing general guidelines on SEA procedure to be completed in the next period. Preparation of guidelines in progress for Armenia, Georgia and the Republic of Moldova  |
| IV.6. Preparation of a video to raise awareness about and promote application of the Convention. *(Moved from annex II)* | Secretariat, consultants | 2017–2020 | Requires funding: ($35,000–$40,000). | Video on the application of the Convention - completed (in Nov. 2020) with funding from EU4Environment  |

*Abbreviations*: Bucharest Agreement = Multilateral Agreement among the Countries of South-Eastern Europe for Implementation of the Espoo Convention; EIA = environmental impact assessment; IAEA = International Atomic Energy Agency; IAIA = International Association for Impact Assessment; MOP8 = the Meeting of the Parties to the Convention at its eighth session; MOP/MOP4 = the Meeting of the Parties to the Protocol at its fourth session; NGOs = non-governmental organizations; OECD/NEA = Organization for Economic Cooperation and Development Nuclear Energy Agency; SDGs = Sustainable Development Goals; SEA = strategic environmental assessment; tbc = to be confirmed; WG7 = the Working Group on Environmental Impact Assessment and Strategic Environmental Assessment at its seventh meeting; WHO = World Health Organization; WWF = World Wide Fund for Nature.

*a* The financing of the activities foreseen in the budget of the Convention and its Protocol for 2017–2020, as set out in the annex to decision VII/4/III4, is contingent on sufficient funds being made available by Parties through their voluntary contributions to the Convention trust fund.

*b* Through “Supporting Kazakhstan’s Transition to a Green Economy Model”, a European Union-funded multi-stakeholder project for 2015–2018. Funding subject to applicable procedures under the project.

*d* “Greening Economies in the European Union’s Eastern Partnership” (EaP-GREEN), a European Union-funded regional multi-stakeholder project (2013-April 2018). Funding subject to applicable procedures under the project.

e “EU4Environment” is a large EU funded Programme to follow up to the EaP GREEN Programme in the EU’s Eastern Partnership countries for the next 4-5 years. The implementing organizations include three UN organizations: UNECE, UN Environment and UNIDO. In November 2017, the European Commission adopted an “Action Document” confirming the overall funding. The project preparations are ongoing. UNECE has prepared a description of action (DoA) and a proposed budget for the component under its responsibility, with demand driven activities on SEA and transboudary EIA included or related to the Convention and the Protocol workplan. The final EU feedback on the activities and the detailed budget is still expected. The project is expected to start in late 2018/early 2019.

Annex II
List of activities awaiting funding and/or identification of lead countries or organizations for the implementation of the Convention and its Protocol for the period 2017–2020

| *Activity/sub-activities* | *Organizational arrangements/lead countries* | *Time schedule* | *Budget* | *Status* |
| --- | --- | --- | --- | --- |
|  |  |  |  |  |  |
|  |  |  |  |  |
| **I. Compliance with and implementation of the Convention and the Protocol** I.1. Reviews of legislation, procedures and practice and technical assistance in drafting legislation to strengthen Parties’ implementation of and compliance with the Convention and the Protocol. Prompted by the Implementation Committee or requested by Parties themselves, as follows: | Undertaken by external consultant(s), with the support of the secretariat.Including a period in-country examining national legislation and based on earlier reviews, as available. |  | Costs: approximately $25,000 per review, plus in-kind contributions from Parties providing experts and from target country for interpretation. |  |
| (a) Technical legislative advice further to possible Committee initiatives (as decided by the Implementation Committee);  | Supervised by members of the Committee. |  | Requires funding. | No requests so far. |
| (b) Technical legislative advice to Parties to the Convention and/or the Protocol requesting assistance (review of primary or secondary legislation; proposals for amendments). | Lead/requesting country:Kyrgyzstan: drafting of secondary legislation for the application of the Convention and an awareness-raising event to promote the adoption of the amended legal framework. |  | Funding being identified. | No funding identified yet |
| **II. Subregional cooperation and capacity-building to strengthen contacts between the Parties and others, including States outside the ECE region** | To be carried out by lead countries, with support from the secretariat, as needed. |  | Participants cover their own travel and accommodation costs to the extent possible, while host countries cover organizational and venue costs in kind (approximately $5,000–$20 000 per workshop). |  |
| **II.A. South-Eastern Europe subregion** |  |  | In kind contributions/donor funding required. |  |
| II.A.1. Workshop(s) on implementation of the Convention, the Protocol and the Bucharest Agreement in the subregion: workshop to prepare for the first Meeting of the Parties to the Bucharest Agreement. | Lead country: Romania. | tbc | In kind (tbc). | No arrangements nor funding (but Romania confirmed at IS-MOPs its wish to organize a workshop in 2020, subject to identification of funds.  |
| II.A.2. First Meeting of the Parties to the Bucharest Agreement. | Lead country: Romania.  | tbc | No funding confirmed yet. | No arrangements/ funding |
| **II.B. Eastern Europe, the Caucasus and Central Asia (and beyond)** |  |  |  |  |
| II.B.3. Promotion of principles of the Convention and the Protocol in Central Asia and beyond in the context of the recent economic developments in Asia: | Lead/target countries: Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan and Uzbekistan and other countries. |  |  |  |
| Pilot application of the Guidelines on transboundary EIA for Central Asian countries | Lead organization: CAREC (tbc) | tbc | Requires funding: ($100,000-$150,000).  | No funding identified |
| **III. Exchange of good practices**Workshops or half-day seminars within meetings of the Working Group or the Meetings of the Parties on: | To be organized by a lead country(ies) with support from the secretariat. | 2017–2020 | Costs (e.g., for speakers, provision and translation of materials) to be covered in kind by lead countries, to the extent possible (approximately $10,000 per seminar). (Travel costs for countries eligible for financial support and non-ECE countries should be covered from the budget.) |  |
| (a) Application of the Protocol on SEA to climate change adaptation and mitigation; | Lead country(ies) or organization(s) to be identified. With possible participation of the UNFCCC secretariat;  | (a) Application of the Protocol on SEA to climate change adaptation and mitigation; | Lead country(ies) or organization(s) to be identified. With possible participation of the UNFCCC secretariat;  | No funding/lead countries identified at this point. |
| **IV. Promoting ratification and application of the Protocol on SEA and/or the Convention** |  |  |  |  |
| IV.1. Development of good practice recommendations for the integration of climate change mitigation and adaptation measures into plans and programmes through SEA (supported by good practice examples).  | Undertaken by external consultant(s), with the support of the secretariat, involving a survey to gather good practice.  |  | Requires consultant(s) for drafting and funding for translation of the survey and responses to it (approximately $25,000). |  |
| IV.2. Development of guidance on the application of the Protocol on SEA to urban planning. | Undertaken by external consultants, with support from the secretariat, possibly in cooperation with THE PEP, the ECE Housing and Land Management Unit, WHO and the ICLEI network.  |  | Requires consultant(s) for drafting and funding for translation (approximately $25,000). |  |
| IV.4. Pilot SEAs in selected countries, in selected sectors, involving the following activities: (a) Two to three workshops for scoping and the analysis of the baseline impact assessment and the development of mitigation measures and recommendations; (b) Two to three public consultation events; (c) Preparation of the SEA report and training on its quality control.  | Lead/target countries and selected sectors (based on requests by the countries): (a) Russian Federation; (b) Kazakhstan; (c) Tajikistan.In collaboration with the support of an external consultant, national experts and the secretariat, and partner organizations, as relevant |  | Requires funding for pilot ($80,000-$100,000) and for staff costs of a project manager and support personnel, P-3 ($15,000 per month) and G-4 ($8,500 per month). |  |

*Abbreviations*: Bucharest Agreement = Multilateral Agreement among the Countries of South-Eastern Europe for Implementation of the Convention on Environmental Impact Assessment in a Transboundary Context; CAREC = Regional Environmental Centre for Central Asia; EIA = environmental impact assessment; ICLEI = Local Governments for Sustainability; NGOs = non-governmental organizations; SDGs = Sustainable Development Goals; SEA = strategic environmental assessment; SEA Resource Manual = Resource Manual to Support Application of the Protocol on Strategic Environmental Assessment (ECE/MP.EIA/17); THE PEP = Transport, Health and Environment Pan-European Programme; tbc = to be confirmed; UNCLOS = United Nations Convention on the Law of the Sea; and WHO = World Health Organization.

Annex III
List of additional activities related to the workplan for the implementation of the Convention and its Protocol for the period 2017–2020

| *Activity/sub-activities)* | *Organizational arrangements/lead countries* | *Time schedule* | *Budget* | *Status* |
| --- | --- | --- | --- | --- |
|  |  |  |  |  |  |
|  |  |  |  |  |
| **Preparation and servicing of an intermediary session of the Meetings of the Parties to the Convention and the Protocol (IS-MOP and IS-MOP/MOP)** | Secretariat with the Bureau and the Working Group | 5-7 February 2019 | $ 30,000 (travel support to eligible countries and NGOs) from the operating reserve | Completed. IS-MOP and IS-MOP/MOP held on 5-7 February 2019 in Geneva, Switzerland.  |
| **Compliance with and implementation of the Convention and the Protocol**  |
| **Drafting of guidance on the applicability of the Convention to the lifetime extension of nuclear power plants**  | Drafted by the ad hoc working group of volunteering Convention Parties, co-chaired by Germany and the UK, in consultation with the relevant intergovernmental and non-governmental organizations, and with support from the secretariat.As mandated by the Working Group, and the IS-MOP, the ad hoc group pursues its work to draft guidance based on the ToR adopted by the Working Group in May 2018 | Interim progress report to IS-MOP in February 2019; Updates to the Bureau and the Working Group’s 8th meeting in 2019Draft submitted to WG9 in 2020. To be submitted for adoption by MOP-8 in 2020 | In-kind by the contributing Parties | Drafting ongoing. Progress reported to IS-MOP and WG8. Draft to be commented by WG9 in August 2020, and to be finalized for MOP-8. Ad hoc group, led by Germany and UK, met **in 2018**: 3rd, Berlin, 20-21 June; 4th: London, 2-3 October. **In 2019**: 5th: Geneva, 25-26 March; 6th: Lisbon, 3-4 June 7th: Netherlands, 8-9 October; 8th: Vienna, 3-4 December**The 2020** meetings were cancelled (due to COVID-19):9th: Rome, 2-4 March 10th: Sofia, 27-29 April; 11th (Espoo, 23-23 June) and replaced by written commenting and on-line consultations.The Co-Chairs consulted NGOs in December 2017 in August + December 2018 and in June 2019; and facilitated a stakeholder workshop (Vienna, 2 December 2019), with invited speakers from NGOs, IAEA, IAIA and Aarhus Convention.  |
| **An international workshop on environmental and health impacts of lifetime extension of nuclear power plants** (to support the preparation of the guidance by the ad hoc working group) | IAIA, in cooperation with the secretariat  | 5 June 2019 (Lisbon) back to back with the 6th meeting of the ad hoc working group. | Mainly, in kind. | Completed. Presentations and conclusions available on Convention website. |
| **Technical legislative advice to Parties to the Convention and/or the Protocol** requesting assistance (review of primary or secondary legislation; proposals for amendments). | Undertaken by external consultant(s), with the support of the secretariat.(a) Kazakhstan: drafting secondary legislation on EIA linked and an awareness raising event to promote the adoption of the legislation (as a follow-up to activities under item I/7 (a) in Annex I, subject of additional confirmation by the Government) |  | Costs: approximately $40,000-60,000 per drafting process | (a) Completed OSCE was a lead partner. Drafts secondary legislation developed (with funding from OSCE and the Government of Switzerland). Transmitted to Kazakhstan in August 2019 ; Additional assistance provided in September/October 2020 to review the second draft of the EIA and SEA chapters of the Environmental Code (with finding from Switzerland)  |
| b) Tajikistan and Uzbekistan: (i) drafting of amendments to the primary legislation and draft secondary legislation for the application of the Convention and the Protocol;(ii) an awareness-raising event to promote the adoption of the amended legal framework (as a follow-up to activities under item I/7 (c) in Annex I, subject of additional confirmation by the Government) |  | Funding from Germany, Switzerland and OSCE: USD approx. 130,000 | (b)(i) Legal drafting**Uzbekistan Completed.**Fact finding mission, Tashkent 1 August 2019;Training workshop, Tashkent, 19-20 August 2019;Final consultation event Tashkent, August/September 2020 (postponed due to coronavirus pandemic, expecting a confirmation by the Government of the possibility to complete event online in October 2020)**Tajikistan:** Completed, as follows: Training workshop, Dushanbe, 10-11 October 2019; Legal drafting initiated in November 2019 and completed in April 2020, based on the results of two events held in Dushanbe: Consultations with national and international experts on the development of the National Environmental Code (6 March 2020)Presentation of the project results to the national stakeholders (15 - 16 April 2020)  |
|  | (c) Uzbekistan: preparing a Road Map for introducing EIA system in line with the Convention |  |  | (c) Completed with funding from Switzerland |
| **Promoting ratification and application of the Protocol on SEA and the Convention** |
| Final publication on lessons learned from EaP GREEN funded technical assistance to support establishing modern environmental assessment systems in selected countries of Eastern Europe and the Caucasus | Undertaken by external consultant(s), with the support of the secretariat | 2018 | Funded by EaP GREEN | Completed: A draft publication prepared in January 2019. Issued as an informal publication in 2020 |
| National training scheme (mainly) for SEA and EIA practitioners | Undertaken by external consultant(s), with the support of the secretariat. | 2018 – 2020  | Requires funding ($50,000–$100,000 per country).Could be funded/partially funded by EU4Environment | If need confirmed by some beneficiary countries (instead of individual training events), could be implemented with EU4Environment  |
| Pilot SEA  | Lead/target country: BelarusSelected sector/plan: draft National Water Strategy in the context of climate change until 2030Undertaken by external consultant(s), with the support of the secretariat and in cooperation with the UNECE Water Convention Belarus | 2019 | Funded/co-funded by “European Union Water Initiative plus for Eastern Partnership Countries (EUWI+) | Completed in 2020. |
| Web-based SEA/EIA databases or information systems  | Undertaken by external consultant(s), with the support of the secretariat. | 2020 (or 2021-22) | Requires funding ($100,000–$150,000 per country). | Development of a model for a SEA database to be funded for the 6 beneficiary countries through EU4Environment planned to be initiated in 2021. |
| Promotion of principles of the Convention and the Protocol in Central Asia and beyond in the context of the recent economic developments in Asia: | Lead/target countries: Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan and Uzbekistan and other countries.To be implemented by OSCE |  |  |  |
| (a) Awareness raising event on SEA(b) Study-tour to Germany to learn about the German SEA system(c) Needs assessment exercise for preparation of the capacity-building strategy on SEA(d) Pilot application of SEA | (a)-(c) Lead/target countries: Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan (tbc) and Uzbekistan (d) Lead/target countries: Kyrgyzstan  |  | USD 260,000  | Initiated with funding from Germany, UNECE and Switzerland:(a) Sub-regional (inception) meeting, Vienna 16-17 October 2019 (completed). National events planned in September/October 2020 in: - Kazakhstan - Kyrgyzstan - Tajikistan - Turkmenistan - Uzbekistan (b) Study Tour, Berlin 2-6 December 2019 (Completed)(c) Needs assessments (ongoing) and national workshops January- June 2020;(\*) Final conference Last week of October/First week of November 2020, Tashkent (tbc);(d) Cancelled |
|  |  |  |  |  |

\_\_\_\_\_\_\_