## Slide 1: The Joint ECE-Eurostat programme on the new recommendations for the 2010 round of Population and Housing Censuses in the ECE region
Joint ECE-Eurostat Steering Group
on Population and Housing Censuses
Objective of the programme:
Preparation of the new Recommendations for the 2010 Censuses of Population and Housing in the ECE Region
To be approved by the Conference of European Statisticians in June 2006 (as decided by the CES in 2003)

## Slide 2: Background
Joint ECE-Eurostat Work Session on Population and Housing Censuses, in May 2003: tentative work plan for updating the „Recommendations…”, with the deadline of approval by the CES in June 2007
Setting up a Steering Group on Population and Housing Censuses (ECE, Eurostat, Canada, Ireland, Russian Federation, Turkey, UK, USA)
June 2003: request by the CES to speed up the work, and finalise the new recommendations before 2007
Revision of the timetable: new deadline for submitting the updated set of recommendations in June 2006

## Slide 3: Work plan for the preparation of the new census recommendations:
Jan. 2004: First meeting of the « Steering Group » and definition of the tentative work plan
March 2004: Questionnaires sent out to ECE member countries
 Oct. 2004: Preparation of various reports on the basis of the results of the questionnaires
Nov. 2004: Joint ECE-Eurostat Work Sessions to discuss general directions for the new recommendations
 May 2005: Preparation of the first draft version of the new recommendations
Nov. 2005: Joint ECE-Eurostat Work Sessions to discuss the text of the new recommendations
Oct. 2005: Second draft
 March 2006: Preparation of the final version of the new recommendations (Steering Group
June 2006: Approval of the new recommendations by the CES
Dec 2006: Publication of the document

## Slide 4: First meeting of the SG in January 2004 Proposed changes to the recommendations for 2010:
Extended section on census methodology and technology covering topics like:
  Possible uses of registers for population censuses
  Possible use of sampling procedures
  „Rolling” censuses
  Publicity campaign
  Evaluation of coverage and quality of census
In-depth revision of selected sections of the recommendations, including:
  Families and households (special Task Force)
  Migrations (ECE/Eurostat (SG on Migration Stat.)
  Place of usual residence (SG on Pop. and Hous. Cens.)
  Institutional households
  Economic characteristics
  Others: income, (ethnic) nationality, language, civil partnership, health and disability, elderly issues
Without setting up additional formal groups
Elimination of the tabulation programme (?!)

## Slide 5: The ECE questionnaire
Preparation and shipment (March 2004) of the questionnaire to countries on the extent of their compliance with the 2000 recommendations
Come-back of the questionnaires in April-May, and their processing and evaluation in May-November by the Steering Group and the Task Force on Families and Households
Preparation of reports on the methods and definitions used in censuses, as well as on future plans: basis for discussion at the present meeting
Approval by the Steering Group of the Agenda of the present sessions, and of the one-day seminar on new (alternative) methods as against traditional census taking

## Slide 6: Present and future activities
Presentation by ECE and Eurostat of their work plan for preparing the new set of joint Recommendations at the meetings organised by UNSD in New York, September 2004 – coordination of census related activities at global level
Expectations with respect to the present 3 Geneva meetings: structure and content of the new recommendations; procedures to be followed; decision on „who does what”; ideas on the expanded methodology chapter
December 2004-May 2005: first draft by working groups and experts
April 2005: Joint ECE-Eurostat Work Session on Registers and Administrative Records for Social and Demographic Statistics: possibly feed into the new census recommendations
November 2005: Meeting on Population and Housing Censuses in view of discussing the draft and reaching a quasi-final version
December 2005-March 2006: new recommendations finalised by ECE, Eurostat and the SG
June 2006: final draft submitted to the CES for approval and, then for publication.