## Slide 1: Overview of the SNA Update
Carol S. Carson
Project Manager
Joint Meeting on National Accounts
SNA Update Session
April 25-28, 2006, Geneva

## Slide 2: Plan of the presentation
Past: Getting started on 1993 SNA, Rev. 1
Present: Progress to date
Future: Key points about the drafting and review phase of the Update

## Slide 3: Past: Key dates
1990s background: incremental updates of the SNA
2003: Statistical Commission called for an update of the SNA
  Process: ISWGNA to coordinate and manage with the assistance of the Advisory Expert Group (AEG)
  Substance: Align the SNA with the new economic environment, advances in methodological research, and needs of users
    But not recommend fundamental changes
    Aim for consistency with other manuals

## Slide 4: Past: key points (cont’d)
2004: Statistical Commission approved a work programme
  Process
    Issues had to meet specified criteria
    Issues were to be researched and proposals developed by topical expert groups
    AEG was to provide advice on issues
    AEG recommendations to be circulated to countries
  Schedule
    Consolidated recommendations for March 2007
    Draft of Rev. 1 for March 2008

## Slide 5: Present
In sum: process worked well so far
  see Progress Report at Project website http://unstats.un.org/unsd/nationalaccount/snarev1.asp
  Statistical Commission expressed satisfaction
The AEG has reached recommendations on almost all points of the 44 agreed issues
  Issues papers and reports of the meetings are at the Project website
  A full set of provisional recommendations will be discussed over the next few months

## Slide 6: Present (cont’d)
Finishing up the issues-oriented phase: two new pages on the Project website
  Consistency
    Lists several known topics where examination of consistency is needed and invites comments
    Other issues may be added in coming months
  Long-term research agenda: identifies issues that were out of scope for this Update and lays ground for further research

## Slide 7: Future: drafting and review
Key points:
  Basic structure of Rev. 1
  Roles of Editor and reviewers
  Organization of the drafting and review
  Key dates
  Outlook

## Slide 8: Basic Structure of Rev. 1
Basic structure will not be changed
  New material will be introduced throughout existing chapters
  Major new topics will have stand-alone chapters, introduced so as to limit disruption
Opportunities to shorten existing text will be exploited—so far, not easy to identify
Record of changes to existing text will be made

## Slide 9: Basic Structure of Rev. 1 (2)
Selected features
  Chapters on some important new material
    Government and the public sector
    Integrated accounting for capital
    Informal sector
  References to other publications for more detailed information
  And more in prospect on tables, glossary, etc.

## Slide 10: Roles: Editor and reviewers
Editor: draft most new text or, if text is contributed by others, bring it into line
Reviewers
  ISWGNA: Support the Editor and provide substantive review of all chapters
  AEG: review chapters
  And, of course, chapters will be posted on the Project website for comment by countries

## Slide 11: Organization of drafting-review
Most chapters will go through at least 4 stages:
0 Existing text or contributions as provided
1 Draft from Editor, followed by “eagle eye”
review by ISWGNA
2 Draft from Editor ready for substantive, wide
review and comment
3 Redraft from Editor, followed by “eagle eye” and substantive review by ISWGNA
4 Draft ready for SC
???

## Slide 12: Organization of drafting-review (2)
Overall scheme: divide chapters into roughly two equal tranches and proceed through with one and then the other
  First tranche: chapters that are the “heart” of the SNA
  Permits timely review and approval of “heart”
Editor will work on blocks of related chapters within a tranche and, when work on a block is completed, turn it over for review

## Slide 13: Organization of drafting-review (2)
Monitoring progress: Three levels, with different purposes, including one on the public website:
  summary chapter x issue matrix with cells changing color to show progress through stages
  Links to draft chapters ready to review

## Slide 14: Key dates
Initial set of recommendations with updated descriptions of issues. Early 2006
Views on consistency, etc. April-Sept. 2006
  Joint NA meeting, Geneva, April 25-28
  IARIW SNA Update sessions, Finland, August
  Other?
Set of recommendations to SC. Late 2006
Draft of “heart” of Rev. 1 for AEG meeting. Early 2007
Draft of rest of Rev. 1 for AEG and wider meeting on implementation. Late 2007
Draft of 1993 SNA, Rev. 1 to SC. Late 2007

## Slide 15: Outlook
Daunting amount of work ahead, with some risks
Monitoring system will be critical in identifying need for strategic adjustment
Manageable task with the continued good will and support of the international statistical community that has been evident so far

## Slide 16: Thank you
Contact:: ccarson@imf.org