## Slide 1
Planning for SNA93 Rev 1 The Canadian Case
Geneva
April 23rd, 2008
Agenda item 3
Invited paper 19

## Slide 2: Steering Committee
Membership
  Ass. Chief Statistician, DG of SNA
  Five SNA directors
    GDP – supply-use
    GDP – sector accounts
    Balance of payments
    Government financial statistics
    Environment accounts
  Two representatives from survey divisions

## Slide 3: Steering Committee
Functions
  Direction on concepts and methods
    Scope of project
  Trade offs
    Accuracy vs. budget
    Integration issues
  Communication with users
    Major users e.g. central bank
    Economic and business associations

## Slide 4: Software
Strategic direction at Statistics Canada is move to more “off-the-shelf” and own account “generic” software
  SAS / databases (SQL, Oracle)
  FAME for some applications
  Moving to warehouse approach
    Integration
    Analysis
  Standard classifications become crucial

## Slide 5: Staff Focus
Recruitment and retention
  Continuous recruitment
  Communities of practice
Training
  Recruits vs. mid-level hires
  Basic concepts vs. methodology
  Continuous training (canned modules)
Getting them involved
  STCWiki

## Slide 6: Key Issues
New concepts
  R&D capitalization
  Goods for processing and merchanting
Changing structure of the economy
  Services sectors
  Globalization issues
Time series consistency
Consistency across macro accounts

## Slide 7: Time frame
Consultations with data suppliers
  Summer 2008
Decide on recommendations to implement
  Spring 2009
Establish revised methodologies
  Fall of 2010
Release of revised estimates
  Spring 2012

## Slide 8: Opportunities
Update concepts and methods
Introduce new data sources
Extend the scope of the accounts
Improve integration of macro accounts
Strengthen employee training
Strengthen communication with users