## Slide 1: Task Force for Measuring Sustainable Development (TFSD)- Project plan
Rutger Hoekstra and Jan Pieter Smits

## Slide 2: Time Line
Sept
2009
March
2010
Sept
2010
Sept
2011
March
2011
Final
report-
Preliminary version
Issue
papers
Virtual conference
Conference
Final
report-
1st draft
Conference
Final
report-
1st draft
Conference

## Slide 3: Towards a first draft of the final report
Sept 2009: This meeting
  Identification of issues/authors
    Session Wednesday (11:20-12:30)
    Session Thursday (15:50-17:30)
  Examples of issues:
    A framework for social capital
    Human capital according to the J-F framework
    A broader set of human capital indicators
    A set of SDI’s based on the capital approach
    The importance of time use
    Global capital stocks
    Natural capital
    The limits of monetization
    Etc. etc etc.
March 2010: Virtual conference about issue papers
  Deadline: March 22nd
  Open for comments for 2 weeks
June 2010: Preliminary verison of final report
Sept 2010: Conference
  Discussion on first draft of the final report