## Slide 1: Managing Metadata System Projects; Experiences of the Czech Statistical Office
Joint UNECE/Eurostat/OECD work session on metadata Geneva, 3–5 April 2006 Ebbo Petrikovits
ebbo.petrikovits@czso.cz

## Slide 2: Brief history
First metadata project in early 1980s
Several attempts were made but all of them failed
Initiative came from the IT branch only
Less cooperation with subject-matter statisticians and methodologists
Project was not approved by the top management of the office

## Slide 3: Lesson Learned
Metadata project started in the IT department without clear and accepted vision
Subject-matter statisticians were not involved in the project – their support was missing
Organizational framework for the project was not specified
Top management was not well informed on the project – its support was very low
Limited general knowledge of the project inside the office

## Slide 4: New Management Policy
In 2003 introduction of new policy for development and implementation of key statistical tasks
Top management defined the development tasks and methods of project management
Development projects:
  Reform of Statistical Survey System (approved Feb 2005)
  Public Database (approved 2004)
  Statistical Metainformation System - SMS (approved Feb 2005)

## Slide 5: Management of the SMS project
3-level management hierarchy
  SMS project teams
    participants: suject-matter statisticians, metodologists
      IT experts, meber od the SMS Unit
  SMS Task Force
    participants: heads of project teams, representatives of middle management, head of the SMS Unit (chairs the meetings)
  SMS Steering Committee
    participants: directors of subject-matter deparments, director of methodology department, head of the SMS Task Force
    1st Vice-President chairs the Steering Committee

## Slide 6: Major finding (1)
Permanent supervision of the SMS project by the top management is necessary precondition for successfull story
Regular follow-up of their SMS development and reporting on the results are important part of the project management
Systematic cooperation with statistical subject-matter experts is inevitable

## Slide 7: Major finding (2)
Focus on the subject matter topics and use of SMS tools in statistical practice is advisable
Importance of training and transfer of SMS know-how.
The SMS methodology and organization of the work must be addressed
User benefit should be clearly presented

## Slide 8: Major finding (3)
Sharing information and knowledge between project teams is necessary (the intranet proved highly effective for this)
Wide availability of information about SMS development to statistical staff have brought positive results

## Slide 9: Thank you for your attention