## Slide 1: Use of Hand Held Computers in United States 2010 Census: Lessons Learned So Far
Andrea Grace Johnson
United States Census Bureau
UNECE
Conference of European Statisticians
Group of Experts on Population and Housing Statistics
Astana Kazakhstan June 4-6 2007

## Slide 2: Background on the U.S. Census
Mandated by our constitution
Every 10 years in years ending in “0” since 1790
Persons are counted at the household they “live or stay” as of April 1 of Census Year
Captures the following data items for each person in the household:
    Sex
    Age
    Hispanic Origin
    Race
    Relationship to Householder
    Housing Tenure (for household)
Notes: Started in 1790
Law states counts are to be delivered to president by end of Census year
Census drives our political representation
Last Census 2000, next 2010
Live or stay is where you are most of the time – does not included temporary
Students counted at university,

## Slide 3: Steps to Conduct U.S. Census
Update Household Inventory
Enumerate
  Deliver Questionnaires
  Nonresponse Followup
Perform Quality Checks
Conduct Data Processing
Provide Initial Results to President by December 31st of Census Year
Notes: [before any #s]
This is a generalized view of the steps involved in taking a census.
Canvassing:
One year before Census Day
Visit or “canvass” every square mile of the U.S
Update the existing inventory of U.S. living quarters
Enumerate:
Use living quarter inventory to deliver questionnaires
Most respondents mail in questionnaires = “self enumeration”
Enumerate
  Non responders
  Other populations
Quality Checks
Double Checks
  Ensure everyone was counted
Independent Quality Checks
  Ensure “overall quality” in the Census count
Data Processing
Process census forms/ enumerations
Process other types of collected data
  Geographic data
  Quality data
  Other types of data
Release counts to the president
[after #1]
At the Census we have what is know the “Master Address File”. This is a list of all know housing units within the U.S.. As part of decennial census we update this file in 2009 so that the list is accurate for the 2010 census.
[after #2]
Depending on the kind of address for the household, we will either mail the forms, or drop them off in person to most of the households in the U.S.. There are some exceptions I will be discussing these shortly.
[after #3]
Once a person receives a form it is up fo theme to fill out the form and mail it back to us. If they don’t we will make a visit
[after #4]
We will make many attempts to try to get information from the household that didn’t respond. If we are unsuccessful at contacting the residents of a household we may contact a neighbor, landlord or other knowledgeable person to obtain the census information for that household.
[after #5]
For people living in dorms, on military reservations, in nursing homes, shelters and in hard to reach areas such as Alaska the Census will not mail out a form but will conduct Census interviews in person.
[after #6]
In the summer of 2010 we will conduct several operations to double check that we did not miss any addresses or add them twice.
[after #7]
We also conduct a series of operations that ensure the accuracy of the data we collect
[after #8]
Once we have finished all of the Census operations, we compile the data. This process takes about ____.

## Slide 4: Other U.S. Census Facts:
2000 Census
  500,000+ temporary workers
  paper forms and scanning processes
  281.5 million
2010 Census
  500,000 + temporary workers
  hand held computers
  ???? Million?
Notes: Largest peacetime effort for the federal government
Over 500 temporary offices are established
  Open for less than 2 years
Over 500,000 temporary employees are hired
  Work for an average of 6-8 weeks.

## Slide 5: 2010 Hand Held Computer Hardware
Internal GPS
Antenna
Internal Cellular
Antenna
Six direct navigation
functions for
most popular functionst
SD Memory Card Slot
with captive protective cover
High Brightness Screen
with anti-glare coating
(almost 2x brighter than
Dell Axim X51)
Soft Power On/Off Button
Finger Print Reader for
Biometric Authentication
4 Way Navigation buttons
with center execute
Tri color LED indicator
Power plug, mini-USB, RJ-11
With captive protective cover
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6: Where are we in 2007?
Awarded contracts
Develop Census Systems
Conduct Dress Rehearsal
Census Activities Start April 2009

## Slide 7: Lessons Learned So Far…

## Slide 8: Lesson 1: It Takes Time.
Planning for 2010 began in 2000:
Feasibility studies/ tests
Budget Evaluations
Development of
  Contract Scope
  Requirements
  Statement of Work
Select Contractor
….and then start software development.
Notes: Conversion is complex and takes time:
Even making decision to go towards a handheld took time
Determining scope of work for what needed to be done
Testing Methodology
Several Feasibility Studies
Large Scale Tests
Finding Funding
Asking for money many years in advance without knowing what would be needed
It took over two years to develop a statement of work to allow contractors to bid, and then several months to evaluate bidding contractors proposals.
Now that the contract is let, it has taken a while to get used to working with the contractor.
All of these activities require iterations of critical thinking to ensure that someone has thought of what will happen, what might happen, and what shouldn’t happen.

## Slide 9: Lesson 2: Don’t Automate Questionnaires Automate Data Collection.
Pre-fill data fields and/or dropdowns
Build in consistency checks
Use technology to its fullest
  GPS
  Cellular Functionality
Notes: Prefilled not only standard data fields but
Careful about mode consistency
Edit checks on age in particular very successful – in an earlier test research indicates that the age edit check was invoked 23% of the time for enumerators, and 77% of the time the age calculated by the HHC, using birthdate of person in question, was the correct age.
GPS not only provides accuracy about where data was collected, it can help ensure that the enumerators are in the right place – aids in their navigation. Over 90% of users sampled from previous census tests stated that GPS helped them locate a followup household.

## Slide 10: Lesson 3: Don’t Underestimate the User.
Users enjoy working with the hand held
Non-technical users could learn to use a hand held.
Usability evaluations are very necessary
Notes: Overall users have been enthusiastic about using the hand held to conduct their census field activities. In a survey of users only 3.7% felt unfavorable about the use of the hand held.
Users from previous censuses like the hand held
While non technical users could learn to use the hand held – its introduction did make the job of the field supervisors more complicated.

## Slide 11: Lesson 4: Automation Can’t Replace Interpersonal Communication.
Daily in-field meetings between supervisors and workers are still needed
  Resolve technical problems
  Ensure quality and progress
  Discuss intended work behavior

## Slide 12: Lesson 5: Hand Held Computers Don’t Necessarily Save as Much Office Space as You’d Think.
Anticipated local office space savings not found
  Locked storage required for hand held computers
  Printers and paper still needed
  Peripheral IT equipment to support training etc.

## Slide 13: Lesson 6: Training Presents New Challenges and Opportunities.
Training development dependent on software development
Use of computer based training (CBT)
Additional materials required for training sessions

## Slide 14: Thank You