## Slide 1
UNECE Group of Experts on Population and Housing Censuses
Marc Hamel
May 25, 2012
Internet Data Collection in the Canadian Census of Population

## Slide 2: 2006 Census experience
Introduction of Internet Response Channel in the 2006 Census
  18% take up
Introduction of central mailout
  Mailout to 73% of dwellings
  Central to the approach used in Canada
Multi-mode collection
  Important changes to roles of enumerators

## Slide 3: 2011 Census objectives
Build on the successes of 2006
  Internet response objective of 40%
  Expand mailout to 80%
  Adapt the collection methodology to maximize internet response without increasing non-response

## Slide 4
How did we do it?

## Slide 5: Key Components
Wave methodology promoting Internet response
An automated system to enable Canadians to call for a paper questionnaire
Master Control System
Wave modelling for daily monitoring and active management of operations

## Slide 6: 1. Wave Methodology
Wave Methodology initiated for 2011
  To increase the returns by Internet without impacting non-response follow-up workload.
Concept of Wave Methodology:
  Multiple contact approaches to encourage response
  Sent out a letter instead of a questionnaire (Wave 1). No immediate option for paper response but the letter must provide an effective method to request a paper questionnaire.
  As the returns from Wave 1 start to decline, sent out a reminder letter to those who didn’t respond (Wave 2).
  As the returns from Wave 2 start to decline, sent out a questionnaire to dwellings that are still not responding after the first two waves (Wave 3).
  Start non-response follow-up after the returns from the questionnaire mail-out start to decline (Wave 4).
  Aligned public communication messages.

## Slide 7: Collection Methodology Mail-out Areas (79% of dwellings)
Wave 1: 7 days before Census Day (May 3)
  75% mailed a letter (Group 1)
  25% mailed a questionnaire (Group 2)
Wave 2: starting Census Day (May 10)
  Reminder letters mailed to all non-responding dwellings in mail-out areas.
Wave 3: starting 8 days after Census Day
  Questionnaire packages mailed to all non-responding dwellings that received the Wave 1 letter (Group 1) (May 18)
  Non-responding dwellings that received a Wave 1 questionnaire (Group 2) received a Voice Broadcast message via telephone if they had a telephone number on the MCS. (May 24-25)
Wave 4: starting 22 days after Census Day (Jun 1)
  Regular non-response follow-up started in mail-out areas
  If no contact made, left a “Notification of Visit” card or a message on the answering machine

## Slide 8: Collection Methodology List-Leave Areas (19% of all dwellings)
Wave 1: starting 8 days before Census Day (May 2)
  Traditional drop-off
Wave 2: starting Census Day (May 10)
  Reminder cards delivered to all list/leave dwellings as unaddressed mail
Wave 3:
  No event for List/Leave, start of wave 4
Wave 4: 10 days after Census Day (May 20)
  Regular non-response follow-up started in list/leave areas

## Slide 9: 2. Questionnaire Request System (QRS)
  The QRS is a 24/7 telephone service allowing a caller to request a paper questionnaire using their secure access code (SAC)
  Toll free telephone number provided on the Wave 1 letter and on the Wave 2 reminder letter sent to all non-respondents in Mail-out areas
  Caller enters 15-digit secure access code
  Code is validated and transmitted to MCS which then transmits address details to Canada Post
  Canada Post addresses and links the pre-packaged questionnaire
  Linked file is updated on the Master Control System (MCS)

## Slide 10: 3. Master Control System (MCS)
A list of all dwellings in Canada to which a questionnaire would be mailed or dropped off
  Source of addresses for mail-out is the Address Register (AR)
  Had a record for each dwelling with a mail-able address.
  Had a record for each estimated dwelling in list/leave areas (no address available)
Central system that integrated information from other collection and processing systems.
Each record given a unique frame-id and a secure access code
Monitored the status of each dwelling through collection (Canada Post, internet submissions and NRFU) and processing
MCS provided daily updates to the MIS for “almost real-time” reporting of work in progress

## Slide 11: 4. Wave Model
Required a tool for planning purposes
Created a mathematical model to represent the implementation of the wave methodology for 2011 operations
  Used for estimation and scenario building (plan numbers for MIS)
  Plan numbers based on daily returns and live test in 2006 census, guestimates and 2009 Census Test
  Implemented in an Excel workbook – not user friendly
  Main uses – provided the planned daily and cumulative volumetrics for printing, collection and processing
  Was further enhanced to include planned field work efforts. Actual MIS was incorporated throughout operations to make the model more “dynamic”

## Slide 12
Results

## Slide 13: 2011 Collection Response Rates
The internet was the primary mode of response for Canadians.

## Slide 14: Results
The Wave 1 letter resulted in a higher response by Internet compared to receiving a questionnaire
There was an effect from Wave 2 and Wave 3 that mitigated the risk of higher NRFU caused by sending out only a letter
An effective Automated Questionnaire Request System (QRS) was implemented allowing callers to call for a questionnaire to be mailed to them.

## Slide 15: Response Rates by Collection Method - mailout

## Slide 17: Census Item Non-response Rates

## Slide 18: Lessons Learned
Wave methodology an effective approach resulting in high Internet response.
Gap between waves was not long enough
Accuracy of mail-out file is paramount
Better tools and training for Census Help Line (CHL) operators
  Better access to dwelling history (field staff and CHL)
Some Canadian do not use traditional mail services

## Slide 19: Live Test – Switch Methodology
 | Response mode |  |  |  | Non-response | 
Collection method | Mail | Internet | CHL | NRFU |  | Total
G1 - Letter | 16.3% | 71.6% | 0.7% | 9.1% | 2.3% | 100.0%
G1 - Questionnaire | 53.3% | 32.3% | 0.5% | 11.6% | 2.4% | 100.0%
G2 - Letter | 23.4% | 57.3% | 1.1% | 15.3% | 3.0% | 100.0%
G2 - Questionnaire | 50.0% | 25.5% | 0.8% | 20.3% | 3.4% | 100.0%

## Slide 20: Contact Information
Marc Hamel
(613) 951-2495
Marc.Hamel@statcan.gc.ca