## Slide 1: 81st UNECE GRPE session PMP IWG Progress Report
G. Martini, T. Grigoratos
Webconf, 9th -11th June 2020
UNITED NATIONS
Informal document GRPE-81-31
81st GRPE, 9-11 June 2020,
agenda item 7
Submitted by the IWG on PMP

## Slide 2: PMP meetings in 2020
2020-01-13: PMP 52nd (GRPE Geneva summary)
2020-04-02 PMP Webconference on exhaust emissions
2020-05-11 PMP Webconference on exhaust emissions
2020-05-20 PMP Webconference on non-exhaust emissions
NEXT F-2-F MEETING: tbd

## Slide 3: EXHAUST PARTICLE EMISSIONS

## Slide 4: Summary of the IWG activity
Proposal for a sub-23 nm particle measurement methodology finalized
Experimental activities on LD and HD
3 informal documents submitted
  Proposal for a sub-23 particle measurement methodology
  Explanatory note on sub-23 particle measurement
  Revised ToR

## Slide 5: Proposal for a sub-23 nm particle measurement
Informal documents GRPE-81-10 and GRPE-81-11
The new proposal:
  Modifies the existing solid PN measurement methodology having a 50% cut-off size at 23 nm (SPN23) in order to allow the use of catalyzed volatile particle remover (VPR) and introduce minor improvements
  Includes as a second option a solid PN measurement methodology with a 65% cut-off size at 10 nm (SPN10).
  The explanatory note describes the main changed to SPN23 and the main elements of SPN10

## Slide 6: Proposal for a sub-23 nm particle measurement
Subject | GTR 15, Annex 5 – Original requirements | Proposed changes for SPN23 | Proposed changes for SPN10 | Reasoning
PNC efficiency | 5012 % @ 23 nm, >90% @ 41nm | None | 6515 % @ 10 nm, >90% @ 15nm | Typical PNC-efficiency, well tested in the field.
Maximum VPR-loss requirement | @ 30nm 30% and @ 50 nm 20% higher than @ 100 nm | None | Addition @15 nm 100 % higher than at 100 nm | No additional requirement below 15 nm since generation of particles < 15 nm challenging, uncertainties high
Polydisperse validation of VPR | a polydisperse 50 nm aerosol may be used for validation | None | Removed | Uncertainties @ 15 nm or below high  test serves no purpose

## Slide 7: Proposal for a sub-23 nm particle measurement
Subject | GTR 15, Annex 5 – Original requirements | Proposed changes for SPN23 | Proposed changes for SPN10 | Reasoning
VPR validation | > 99.0 % vaporization of 30 nm tetracontane particles, with an inlet concentration of ≥ 10,000 per cm³ (Monodisperse) | None | > 99.9 % removal efficiency of tetracontane particles with count median diameter > 50 nm and mass > 1 mg/m3. (Polydisperse) | Secure the functioning of VPR also for PNC with 6515 % @ 10 nm, >90% @ 15nm
Volatile Particle Remover (VPR) | All parts (of SPN-system) -- shall not react with exhaust gas components | - VPR may be catalyzed (both heated evaporation tube and catalytic stripper allowed) | - the VPR shall be catalyzed (use of catalytic stripper only) | Minimize the risk of artefacts for SPN10. Comparability of PNC10 and PNC23 and possibility of using new sampling systems with CS also for SPN23 by fitting a PNC with a D50 @ 23 nm.

## Slide 8: Question addressed by PMP IWG
Could the PN10 emission measurement cover also PN23 emission measurement in regulatory measurements?
  If the vehicle passes the possible future PN10 limits could it be considered to pass also PN23-limit, although PN10 limits may not be valid in the region?
The aim is to avoid double measurements

## Slide 9: Briefly about the experimental Exercises
LD Sub23nm
  Europe done
  Equipment returning from Asia, exercise interrupted due to Covid-19
HD Tailpipe (Investigate the possibility of using direct sampling from raw exhaust and PN10)
  Europe done
  Equipment now in Asia

## Slide 10: Revised ToR
Include on-road PN measurements (PN-PEMS) in the scope of the PMP IWG (request from RDE IWG)
Tasks:
  Submissions of an informal proposal for HD raw exhaust PN sampling and extension of sub-23 nm procedure to HD engines: January 2021
  Submissions of an informal proposal for LD PN-PEMS 10 nm specifications : June 2021

## Slide 11: Procedural issue
  Submissions of an informal proposal for HD raw exhaust PN sampling and extension of sub-23 nm procedure to HD engines
  For LD the PN measurement method was both in Reg. 83 and GTR 15. So it was decided to amend GTR 15.
  The PN measurement method for HD is described in UNECE Reg. 49 and not in GTR 4.
  What approach?

## Slide 12: NON-EXHAUST PARTICLE EMISSIONS

## Slide 13: Brake Emissions – Task Force 1
What were the main activities of TF1 during the last months?
TF1 submitted the Informal Document GRPE-81-XX entitled "Non-Exhaust Brake Emissions — Laboratory testing — Part 1: Inertia Dynamometer Protocol to Measure and Characterise Brake Emissions Using the WLTP-Brake Cycle"
The document is the first part of the overall protocol (PMP Brake Protocol) and addresses items related to the novel WLTP-Brake Cycle and the inertia dynamometer test itself.
Chapter 1 | Chapter 2 | Chapter 3 | Chapter 4 | Chapter 5 | Chapter 6 | Chapter 7 | Chapter 8 | Chapter 9
Purpose | Scope | Normative References | Terms and Definitions | Symbols and abbreviations | General dyno requirements | Adjustment of cooling air | Test Sequence | Test Reports
Describes the purpose of the submitted ID | Describes the scope of the submitted ID | An overview of the documents referenced in the document | An overview of terms related to brake emission measurement | A Table with all symbols and abbreviations in the protocol | Set of minimum requirements that a dyno should meet to run BE tests | Describes how to set cooling air speed in different dynos plus examples | Gives a general overview of the WLTP-Brake cycle | Describes the 2 main outputs of brake dyno tests

## Slide 14: Brake Emissions – Task Force 2
Preparation Phase
Included the decision on the test method approach at the PMP level (brake dynamometer) as well as the merging of sampling and measurement discussion to a common group --- Completed
Understanding Phase
Included the presentation and discussion on existing and state-of-the-art configurations for brake particles sampling and measurement --- Completed
Development Phase
Define a set of min requirements for measuring brake particle emissions. Apply requirements in a RR exercise and come up with final technical specs --- On-going (Expected to be finalized by end Q3/2020)
Parameter 1 | Parameter 2 | Parameter 3 | Parameter 4 | Parameter 5 | Parameter 6 | Parameter 7 | Parameter 8 | Parameter 9
WLTP-Brake Cycle | Background Concentration | Dynamometer Climatics | Temperature Measurement | Bedding-in Procedure | Enclosure Design | PM Measurement | PN Measurement | Other Topics

## Slide 15: Brake Emissions – Task Force 2 – Next Steps
Testing Phase
A RR campaign will take place in the next months. PMP members able to follow the specified requirements can participate. The campaign will start in Q4 2020 and finish by the end of Q1 2021.
  Assess and further extend the defined minimum technical requirements for emissions testing
  Evaluate the repeatability and reproducibility of brake emissions tests under specified conditions
  Use the "lessons learnt" to finalize the methodology for measuring brake particle emissions
Assessment Phase
This phase will include the assessment of the RR results. TF2 will develop the final specifications for the brake emissions measurement method. This task is expected to be completed by Q3 2021
Reporting Phase
Parts 2 "Minimum Requirements and Guidelines for Sampling and Measurement of Brake Emissions for Particle Number and Particle Mass" and 3 "Reporting Test Results from Brake Emissions Testing" of the PMP Brake Protocol will be published at Q4 2021

## Slide 16: Summary of the activity – Future Outlook
One ID submitted: "Non-Exhaust Brake Emissions — Laboratory testing — Part 1: Inertia Dynamometer Protocol to Measure and Characterise Brake Emissions Using the WLTP-Brake Cycle"
Two more to submit: "Minimum Requirements and Guidelines for Sampling and Measurement of Brake Emissions for Particle Number and Particle Mass" and "Reporting Test Results from Brake Emissions Testing"
  Next F2F PMP Meeting to introduce the discussion for possible adjustments of the method to include other technologies (i.e. regenerative braking) and vehicle categories (i.e. vehicles >3.5t) to the general methodology
  Proposal: Organize a PMP-Brake workshop in January 2021 in Geneva during the GRPE week with the purpose of discussing with experts and contracting parties the way towards a method for regulatory purpose

## Slide 17: Tyre Emissions – Summary
H2020 Project
The LC-MG-1-14-2020 call aims in addressing the issue of particle emissions and noise from tyres. It is a 2-stage call and the winning consortium(a) will work among others on the following topics.
  Assessment and characterization of the amounts of tyre particles emitted under different driving conditions both in the laboratory and on-road
  Provide recommendations for the development of reliable and repeatable methodologies for the assessment of tyre emissions and tyre abrasion rate
  Particles tracing and quantification in different environmental compartments with focus on microplastics emissions
Abrasion Rate
ETRMA has completed the feasibility assessment regarding the development of a tyre abrasion methodology. ETRMA has committed to present their proposal at the next F2F PMP Meeting.
PMP's target remains to explore the possible correlation of tyre abrasion rate with PM10 and PM2.5 emissions as soon as the method becomes available

## Slide 18: Keep in touch
EU Science Hub: ec.europa.eu/jrc
@EU_ScienceHub
EU Science Hub – Joint Research Centre
EU Science, Research and Innovation
Eu Science Hub
Notes: Delete/update as appropriate

## Slide 19: Thank you
© European Union 2020
Unless otherwise noted the reuse of this presentation is authorised under the CC BY 4.0 license. For any use or reproduction of elements that are not owned by the EU, permission may need to be sought directly from the respective right holders.
Slide xx: element concerned, source: e.g. Fotolia.com; Slide xx: element concerned, source: e.g. iStock.com
Notes: Update/add/delete parts of the copy right notice where appropriate.
More information: https://myintracomm.ec.europa.eu/corp/intellectual-property/Documents/2019_Reuse-guidelines%28CC-BY%29.pdf