## Slide 1: Status Report of the Informal Working Group on Safer Transport of Children in Buses and Coaches (IWG-STCBC)
Chair: Marta Anglès , SPAIN
Secretary: FARID BENDJELLAL, CLEPA
67th GRSP Session
20 – 13 July 2020
Informal document GRSP-67-08
67th GRSP, 20-23 July 2020 agenda item 15
Submitted by Spain

## Slide 2
1st IWG-STCBC meeting
Date: 9th July 2019 Location: Ministerio de Industria, Comercio y Turismo , Madrid, Spain
Initial discussions & DraftingTerms of Reference.
2nd IWG-STCBC meeting
Date: 30th October 2019 Location: Applus IDIADA, Tarragona, Spain
Reviewing accident surveys , discussing key elements to investigate , Defining a draft Road map.
3rd IWG-STCBC meeting
Date: 16th-17th January 2020 Location: CLEPA, Brussels
Definition of dynamic tests conditions, definition of research key dynamic tests to see the dummy behaviour.
Informal Working Group

## Slide 3: Next Planned Tasks
  Seat belt specifications
  Market overview of seat-belt installation
  Distance between bus/coaches seats in Korea
  Presentation of requirements that apply in Korea to buses/coaches
  Key elements for future accident investigation
  Top and front views from Evobus simulation
  Support leg assessment volume
  Testing
  Comparison of loads in R80 and using M2 pulse in R100

## Slide 4
Road map
2020 | 2021 | 2022
Learning Phase | Execution Phase | Check & Submission to GRSP
Collect data on: accident situations usage conditions space in and testing requirements for M2 & M3 vehicles Define format for accident data collection | Defining key elements of the regulation - Drafting Requirements & evaluating their feasibility and relevance | Completion of proposal to GRSP

## Slide 5: Timeline
11 12
181
182
68
70
67
69
66
3
WP.29
GRSP
IWG
184
183
IWG creation approved
IWG submission of new regulation
Formal Doc.
4
5
Plan and Schedule
Report
6
180
1 2 3 4 5 6 7 8 9 10 11 12
2019
2020
2021
2022
1 2 3 4 5 6 7 8 9 10 11 12
185
186
187
71
Informal Doc.
1 2 3 4 5 6 7 8 9 10 11 12
188
1 2 3 4 5 6
72
189
2023
7
8
9
10
11
12
190

## Slide 6: Next IWG Meeting
4th IWG-STCBC meeting Postponed due to COVID situation
Date: TBD Location: Cologne
5th IWG-STCBC meeting
Date: TBD Location: France

## Slide 7: Thank you for your attention!