|  |  | ECE/MP.EIA/WG.2/2021/INF.4 Distr.: General 25 October 2021 Original: English |
| --- | --- | --- |

Economic Commission for Europe

Meeting of the Parties to the Convention 
on Environmental Impact Assessment 
in a Transboundary Context

Meeting of the Parties to the Convention 
on Environmental Impact Assessment in 
a Transboundary Context serving as the 
Meeting of the Parties to the Protocol on 
Strategic Environmental Assessment

Working Group on Environmental Impact Assessment
and Strategic Environmental Assessment

Tenth meeting

Geneva, 1–3 December 2021

Item 3 of the provisional agenda
Compliance and implementation

Timetable for the modification of questionnaires and the preparation of the draft reviews of implementation

Note by the secretariat

This note is prepared by the secretariat, based on the deliberations of the Implementation Committee at its fiftieth session (online, 4-7 May 2021). It presents a proposed detailed timetable for the modification of the questionnaires for the implementation of the Convention and its Protocol, and for the preparation of the subsequent draft reviews of implementation, in accordance with the workplan for the implementation of the Convention and its Protocol adopted through decision VIII/2–IV/2, annex I, item B 1–3. (See also decision VIII/5 and IV/5 on the review of implementation of the Convention and the Protocol, respectively).

I.	Provisional schedule of Convention/Protocol Body meetings*

| Session | Body | Tentative location | Tentative dates |
| --- | --- | --- | --- |
| 49 | Implementation Committee | Geneva | 2–5 February 2021 |
| 50 | Implementation Committee | Geneva | 4–7 May 2021 |
|  | Bureau | Geneva | 16-17 June 2021 |
| 51 | Implementation Committee | Geneva | 4–7 October 2021 |
| 10 | Working Group on EIA and SEA | Geneva | 1–3 December 2021 |
| 52 | Implementation Committee | Geneva | 1–4 February 2022 |
| 53 | Implementation Committee | Geneva | 10–13 May 2022 |
|  | Bureau | Geneva | 9 – 10 June 2022 |
| 54 | Implementation Committee | Geneva | 4–7 October 2022 |
| 11 | Working Group on EIA and SEA | Geneva | 19 – 21 December 2022 |
| 55 | Implementation Committee | Geneva | 31 January – 3 February 2023 |
|  | Bureau | Geneva | 21-23 February 2023 |
| 56 | Implementation Committee | Geneva | 2–5 May 2023 |
| 12 | Working Group on EIA and SEA | Geneva | 13–15 June 2023 |
| 57 | Implementation Committee | Geneva | 5–8 September 2023 |
| 9 and 5 | MOP and MOP/MOP | Geneva | 12–15 December 2023 |

*The meeting dates for 2023 are preliminary, and expected to be confirmed in summer 2022.

II.	Tasks and time schedule foreseen in the workplan (decision VIII/2–IV/2) and in decisions VIII/5 and IV/5 on reporting and review of implementation

| Method of work (sub-activities) | Organizational arrangements | Time schedule |
| --- | --- | --- |
| Modification of the questionnaires for the report on implementation of the Convention and the Protocol, in 2019–2021, taking into account the suggestions provided for improving the report | Undertaken initially by the Implementation Committee, and the Working Group on EIA and SEA with the support of the secretariat | Presentation of draft modified questionnaires to the Bureau in June 2021 and the Working Group in 2021 (30 November–2 December 2021) |
| Distribution to Parties of the questionnaires for reporting on implementation of the Convention and the Protocol in 2019–2021. | Carried out by the secretariat | Issue of questionnaires by end of December 2021. Return of questionnaires by end of April 2022. |
| Preparation of draft reviews of implementation of the Convention and the Protocol | Carried out by the secretariat | To be prepared in summer 2022. Presentation of the draft reviews to the Committee and the Working Group in autumn 2022 and subsequently, to MOP9 and MOP/MOP5. |

III.	Detailed time schedule for the modification of the questionnaires and the preparation of the draft reviews of implementation

|  | Task | Responsibility | Time schedule |
| --- | --- | --- | --- |
|  | Modification of the questionnaires | Committee members/curators | By IC 50 |
|  | Consideration of the draft modified questionnaires | Committee | 4–7 May 2021 (IC50) |
|  | Consideration of the draft modified questionnaires | Bureau | 16–17 June 2021 |
|  | Revision, as necessary, of the draft questionnaires (on the basis of the Bureau comments) | Committee members (curators)/secretariat | By 1 September 2021 (electronic decision-making procedure) |
|  | Processed and submitted for translation as official documents to the Working Group | Secretariat | In the first half of September |
|  | Presentation of the draft questionnaire to the Working Group | Secretariat | 1–3 December 2021 (10th meeting of the Working Group) |
|  | Revision, as necessary, of the draft questionnaires (on the basis of the Working Group comments) | Committee members (curators)/secretariat | By 20 December 2021 (electronic decision-making procedure, as needed) |
|  | Translation of the possible comments by the WG draft questionnaires | Secretariat | 20 December 2021 |
|  | Distribution of the questionnaire to the Parties to the Convention and the Protocol | Secretariat | By 31 December 2021 |
|  | Completion and return of completed questionnaires | Parties to Convention and Protocol | By 30 April 2022 |
|  | Preparation of the draft seventh review of implementation of the Convention and the draft fourth review of implementation of the Protocol as official documents | Secretariat/Consultant | By 15 September 2022 |
|  | Consideration of the draft reviews of implementation | Working Group on EIA and SEA | 19 – 21 December 2022 (11th meeting of Working Group) |
|  | Revision, as necessary, of the draft reviews | Secretariat | Early February 2023 |
|  | Checking of the revised draft reviews | Bureau | 21–23 February 2023 (Bureau meeting) |
|  | Submission of the draft reviews for translation (as official documents) | Secretariat | Summer 2023 to be submitted as official documents to the MOPs |
|  | Consideration of the draft seventh review of implementation of the Convention and the draft fourth review of implementation of the Protocol | Meetings of the Parties | 12–15 December 2023 (MOP9 and MOP/MOP5) |