## Slide 1: UNECE GRPE Informal Group on Environmental and Propulsion Performance Requirements of L-cat Vehicles (EPPR IWG)
State of Play
Daniela Leveratto
(EPPR IWG Secretary)
Informal document GRPE-84-15
84° GRPE, Nov. 2021
Agenda item 5

## Slide 2: Content
EPPR IWG:
  Meetings
  Work Progress
  Outlook
  Activities at a stalemate

## Slide 3: EPPR meetings in 2021
Face-to-face meetings:
  Due to COVID 19 no f2f meeting were held
Web conferences:
8 January 2021 EPPR 41st (GTR 2 -next step*, Durability)
4 February 2021 EPPR 42nd (GTR 2 -next step*, Durability)
3 - 4 March 2021 EPPR 43rd (GTR 2 -next step*, Durability)
27 - 28 April 2021 EPPR 44th (GTR 2 -next step*, Durability)
27 May 2021 EPPR 45th (GTR 2 -next step*, Durability)
30 June 2021 EPPR 46th (GTR 2 -next step*, Durability)
21 July 2021 EPPR 47th (GTR 2 -next step*, Durability)
26 Aug. 2021 EPPR 48th (GTR 2 -next step*, Durability)
No further meetings planned, in lack of both Chair and Vice-Chair
*next step = amendment 5 to extend the scope of vehicles and fuels

## Slide 4: EPPR work progress
Draft GTR2 Amd.5
Formal document submitted to Jan. 2022 GRPE: GRPE/2022/6
Part II (text) concluded
Part I (Rationale) and Technical Report missing
Draft DUR GTR
Formal document submitted to Jan. 2022 GRPE : GRPE/2022/7
Part II (text) concluded
Part I (Rationale) and Technical Report missing

## Slide 5: EPPR outlook
< June 2022
To get GTR2 Amd. 5 and DUR GTR adopted at June WP29
June 2022 GRPE
Ad-interim report of the IWG to GRPE due, with an outlook on future activities and potential review of the IWG Terms of Reference.
> June 2022 GRPE
As noted in GRPE-83-28 EPPR Status Report at Jun 2021, ref. future activities the IWG is already considering:
  Unified rules and test procedures to measure power and torque for 2- and 3-wheelers
  The transposition of UN GTR 2 into a UN Regulation

## Slide 6: EPPR activities at a stalemate
Leadership Team lacking:
Chair/EC retired end of August 2021
Vice-Chair/Japan concluded his assignment in July
No candidatures submitted so far for the above roles
-> Activities at a stalemate
Candidates?

## Slide 7: Thank you
You can follow us in:
https://wiki.unece.org/display/trans/EPPR+Main+activities
Notes: Update/add/delete parts of the copy right notice where appropriate.
More information: https://myintracomm.ec.europa.eu/corp/intellectual-property/Documents/2019_Reuse-guidelines%28CC-BY%29.pdf