## Slide 1
Status Report of the IWG on Automotive Life Cycle Assessment (A-LCA)
Prepared by
the A-LCA Informal Working Group
Informal document No. GRPE-90-31
90th GRPE, 10 – 12 January 2024
Agenda item 14

## Slide 2
1. Progress of the A-LCA IWG since 89th GRPE
1/7
Held 5 IWG Meetings including one with conjunction to 90th GRPE session
<OUTCOMES>
Successfully started the subgroup activities with constructive contribution by member and with excellent leadership by leaders
Intensive discussion on “Level Concept” and “Overarching Aspects” is on going
Overall schedule
 |  | 2022 |  | 2023 |  |  | 2024 |  | 2025 |  | 
GRPE |  | 86th |  | 87th 88th |  | 89th | 90th | 91st | 92nd |  | 93rd
 |  | Workshop |  |  |  |  |  |  |  |  | 
A-LCA IWG |  |  |  |  |  |  |  |  |  |  | 
 | Overarching aspects |  |  |  |  |  |  |  |  |  | 
 | Develop methodologies |  |  |  |  |  |  |  |  |  | 
 | Drafting |  |  |  |  |  |  |  |  |  | 
Informal Documents
Working Documents
1st IWG Meeting @ Okinawa/Japan
Approved Terms of Reference
Progress

## Slide 3
2. A-LCA Working Organisation
2/7
Production
responsible to SG3
led by Korea, China,
OICA and CLEPA
Material
Acquisition
responsible to SG2
led by Japan
Use Stage
responsible to SG4
led by EC,
OICA and AVERE
End of Life
responsible to SG5
led by China/Japan
Fuel & Energy
responsible to SG6
led by Japan/AVERE
Drafting
responsible to SG7
led by tbd
Develop
Methodology
Develop
Resolution
Manage consistency of each SG and Take care of Common Areas
responsible to SG1
led by Leading Team and SG Leaders

## Slide 4
3. Remarkable Notes (1)
3/7
Agreement
Applicable vehicle : Category 1-1
IWG
Scope of greenhouse gas species : all IPCC AR6 GHG GWP 100 species and Hydrogen
Under the discussion
Level concept and its definition
Indirect infrastructure
Transportation
Definition of “representative vehicle”
Request to SGs
the elements/areas/processes to utilize "secondary data“
future scenario of energy mix
SG2
SG3
Under the discussion
Primary data and quality rating
Level concept and its definition
handover point between SGs
Production relevant emissions
Agreement
Declared unit
Under the discussion
Calculation method
Battery materials
Agreement
Level concept and its definition
Usage of the recycled material
Consider regional carbon intensity

## Slide 5
3. Remarkable Notes (2)
4/7
SG4
SG5
SG6
Agreement
Scope, Boundaries, maintenance + regular consumption
Under the discussion
CO2_equivalent calculation including functional unit
Level concept implementation
Service life duration/mileage definition
In-use data to reflect realistic conditions
Type-approval data + correction
Under the discussion
Methodology of recycling model
Recycle process
Consideration of second life
Boundary conditions
Secondary data set
Agreement
Develop recycling model
Under the discussion
Specificities of the levelling concept
Inclusion of hydrogen
Future carbon intensity
Agreement
Scope of emissions
Functional unit of the subgroup

## Slide 6
4. Next Actions
5/7
Meetings until next GRPE (May 2024)
~ April 2024 : a couple of virtual meeting
18th & 19th April : Hybrid meeting @ Seoul
the week of : Face-to-face meeting @ Geneva
May 20th
Each SG activities including meeting schedule are handled by each SG leader(s)
Main agenda and Expected outcomes
< discuss overarching aspects, review SGs activities
and provide the guidance if necessary>
<finalise overarching aspects, prepare drafting activities, review SGs activities and provide the guidance if necessary>
<review overall progress status,
take off the drafting activities>
request half day session
in conjunction with 91st GRPE session

## Slide 7
5. Current Progress
6/7
Progress level (%) items | 20 | 40 | 60 | 80 | 100 | Notes
ToR |  |  |  |  |  | FIXED with strong leadership by GRPE
 | January 2023 |  |  |  |  | 
Working Organisation including Subgroup structure |  |  |  |  |  | Established 6 subgroups (SGs) 5 SGs are very active with SG leaders initiative
 | May 2023 |  |  |  |  | 
Overarching aspects |  |  |  | January 2024 | January 2024 | Slightly behind the schedule Continue to discuss in parallel with SG activities
A-LCA Methodology |  |  |  |  | March 2025 | Progress of each SG is slightly vary
Drafting |  |  |  |  | June 2025 | Activities will be taken off after June 2024
: target level as of January 2024

## Slide 8
7/7
Thank you!
Leading Team
<co-Chairs>
Tetsuya NIIKUNI : niikuni@ntsel.go.jp
Charyung KIM : cha1052@kotsa.or.kr
<Secretariats>
Erik POSTMA : ep@acea.auto
Romain DENAYER : romain@avere.org
Nick ICHIKAWA : ichikawa@ntsel.go.jp